## User Stories
ISSUE TYPE |  | SUMMARY | PRIORITY | STORY POINT | ASSIGN TO
EPIC NO | STORY NO | REGISTER
Epic 1 | Story 1 | Check Signup button is displayed at https://examples.testsigma.com/ | High | 1 | Reshma K.R
| Story 2 | Check the user is able to navigate to the register page by clicking on Signup Button. | High | 2
| Story 3 | Check the header of the registration page | High | 1
| Story 4 | Check user is able to see "Register to travel account" line | Medium | 1
| Story 5 | Check all the Required fields by filling and not filling any data and Verify if blank spaces are passed in required fields. | High | 1
| Story 6 | Verify the numbers and special characters are not allowed in the Fullname fields. | Low | 1
| Story 7 | Check that the user is able to register with all the valid and invalid email addresses. | Medium | 1
| Story 8 | Check that user is able to register with all the valid and invalid phone number | Medium | 1
| Story 9 | Verify user is able to select one of the Age group in radio button while registeration | Low | 1
| Story 10 | Verify user is able to select one of the gender in radio button while registeration | Low | 1
| Story 11 | Verify user is able to select Hobbies from the checkbox while registration | Low | 1
| Story 12 | Verify user is able to select Interests from the checkbox while registration | Low | 1
| Story 13 | Check all the password validations with all different combinations. | Medium | 2
| Story 14 | Verify user has entered same password in both the password and confirm password section | High | 1
| Story 15 | Check the profile picture button is working or not | Medium | 1
| Story 16 | Check on the click upload button it should ask for the location for upload | Medium | 2
| Story 17 | Check is there any restriction of image file size to upload | Low | 1
| Story 18 | Check whether the image are uploading or not | Medium | 1
| Story 19 | Verify the user is able to register by clicking on register button | High | 1
| Story 20 | Verify that the user is redirected to appropriate page after successful registeration | High | 2
LOGIN
Epic 2 | Story 1 | Check the user is able to navigate to login page | High | 1 | Radha Panchal
| Story 2 | verify if a user will be able to login with a valid username and valid password. | High | 1
| Story 3 | Verify if a user cannot login with a invalid username and an valid password. | High | 2
| Story 4 | verify the login functionality with valid username and invalid password. | Low | 1
| Story 5 | verify the user login with blank username. | Low | 2
| Story 6 | verify the user login with blank password. | Medium | 1
| Story 7 | verify the user is able to fill"password"in the textbox. | Medium | 2
| Story 8 | Verify if the data in password field is either visible as asterisk or bullet signs. | Medium | 2
| Story 9 | check the user is able to click on forget password navigate to the forget password. | Medium | 2
| Story 10 | verify if a user is able to login with a new password only after he/she has changed the password. | Low | 2
| Story 11 | Verify if the ‘Login’ key of the keyboard is working correctly on the login page. | Medium | 1
| Story 12 | Verify if user enter invalid data then user is able to see error message | Medium | 2
| Story 13 | check the user is able to enter valid data & get successfull login. | Medium | 1
SEARCH
Epic 3 | Story 1 | check the user is able to navigate throught Go To Travel button. | High | 1 | Ruchita Sapkal
| Story 2 | check the user can navigate to go to travel page using button. | High | 4
| Story 3 | check the user to display one way flying , round trip flying, multicity butotn. | High | 3
| Story 4 | check the user can navigate to one way flying page using button. | High | 2
| Story 5 | check are you able to city you are going to fly from and fly to. | High | 2
| Story 6 | check the departure button. | High | 2
| Story 7 | check you should enter the date of departing . | Medium | 5
| Story 8 | check number of passengers (adults ,children and infant) and then select class (Economicy ,Premium economy, Business, First Class) then press the Search button. | Medium | 4
| Story 9 | check once you enter all the necessary information and press the Search button, you will be redirected to the page with search results. Here you can find recommended content that matches your criteria a diverse number of flights available. | Medium | 3
| Story 10 | Check from top you can apply the Sort and Filter functionality to find a flight based on your specific needs and requirements. | Medium | 1
| Story 11 | Check the filters are applied in real time that means you don’t need to press the Confirm button to see them applied. Sort and Filter functionality allows you to sort filters that you want to be applied. a. number of stops; b. airlines; c. lowest and highest price; | Medium | 4
| Story 12 | Check once you can press the Reset button to reset all the information selected in one click. | Medium | 3
| Story 13 | Check you have selected the flight, you can press the Apply button. Then you will be shown a range of airlines for returning flights to choose from.and redirected to the trip summary page. | low | 1
| Story 14 | Verify you can see information about the flight, see flight and baggage fee details, change flights if it is necessary and then continue the Booking process. | High | 3
| Story 15 | check the user can navigate to Round Trip Flying page using button. | High | 1
| Story 16 | check the departure or destination toggle button. | High | 4
| Story 17 | check are you able to city you are going to fly from and fly to. | High | 3
| Story 18 | Verify you should enter the date of departing and returning. | High | 2
| Story 19 | check number of passengers (adults ,children and infant) and then select class (Economicy ,Premium economy, Business, First Class) then press the Search button. | Medium | 4
| Story 20 | check once you enter all the necessary information and press the Search button, you will be redirected to the page with search results. Here you can find recommended content that matches your criteria a diverse number of flights available. | Medium | 3
| story 21 | Check from top you can apply the Sort and Filter functionality to find a flight based on your specific needs and requirements. | Medium | 1
| story 22 | Check the filters are applied in real time that means you don’t need to press the Confirm button to see them applied. Sort and Filter functionality allows you to sort filters that you want to be applied. a. number of stops; b. airlines; c. lowest and highest price; | Medium | 4
| story 23 | Check once you can press the Reset button to reset all the information selected in one click. | Medium | 3
| story 24 | Check you have selected the flight, you can press the Apply button. Then you will be shown a range of airlines for returning flights to choose from.and redirected to the trip summary page. | low | 1
| story 25 | Verify you can see information about the flight, see flight and baggage fee details, change flights if it is necessary and then continue the Booking process. | High | 3
| story 26 | check the user can navigate to Multicity page using button. | High | 1
| story 27 | check the departure or destination toggle button. | High | 4
| story 28 | check are you able to city you are going to fly from and fly to. | High | 3
| story 29 | Check you should enter the date of departing and returning. | High | 2
| story 30 | check number of passengers (adults ,children and infant) and then select class (Economicy ,Premium economy, Business, First Class) then press the Search button. | Medium | 4
| story 31 | check once you enter all the necessary information and press the Search button, you will be redirected to the page with search results. Here you can find recommended content that matches your criteria a diverse number of flights available. | Medium | 3
| story 32 | Check from top you can apply the Sort and Filter functionality to find a flight based on your specific needs and requirements. | Medium | 1
| story 33 | Check the filters are applied in real time that means you don’t need to press the Confirm button to see them applied. Sort and Filter functionality allows you to sort filters that you want to be applied. a. number of stops; b. airlines; c. lowest and highest price; | Medium | 4
| story 34 | Check once you can press the Reset button to reset all the information selected in one click. | Medium | 3
| story 35 | Check you have selected the flight, you can press the Apply button. Then you will be shown a range of airlines for returning flights to choose from.and redirected to the trip summary page. | low | 1
| story 36 | Verify you can see information about the flight, see flight and baggage fee details, change flights if it is necessary and then continue the Booking process. | High | 3
Review your Booking
Epic 4 | Story 1 | Check the book now button is working or not | High | 1 | sai prathibha
| Story 2 | check the itienary text is visible or not | Medium | 1
| Story 3 | check the flight details is visible or not | High | 1
| Story 4 | check the arrival and departure details is available or not | High | 1
| Story 5 | Check that baggage details is visible or not below flight details | High | 1
| Story 6 | check the fare summary tab with all details is displaying correctly or not | High | 1
| Story 7 | Check the cancellation and data change is visible or not | High | 1
| Story 8 | Check that in know more information is visible or not | High | 1
| Story 9 | Check that coupon code is entering correct or not | High | 1
| Story 10 | Check that baggage under important information is visible or not | High | 1
| Story 11 | Check that Adds ons text is visible or not below the important information | High | 1
| Story 12 | Check that all benefits are under the Adds on tab | High | 1
| Story 13 | Check that select yes for conform the trip button is selected or not | High | 1
| Story 14 | Check that button thanks for donating is selected or not | High | 1
| Story 15 | Check that continue button is working or not | High | 1
| Story 16 | Check that flight summary text is visible or not | Medium | 1
| Story 17 | Check that flight details link is working or not | High | 1
| Story 18 | Check that traveller details text is visible or not | Medium | 1
| Story 19 | Check that Add adults functionalities working or not | High | 1
| Story 20 | Check the first name and last name is taking the text or not | High | 1
| Story 21 | Check the male or female by clicking the radio button is working or not | High | 1
| Story 22 | Check that contact information is visible or not | Medium | 1
| Story 23 | Check that mobile number and email id entering correct or not | High | 1
| Story 24 | Check that GST number of business travel is visible or not | High | 1
| Story 25 | Check the acknowledgment check box is working or not | High | 1
| Story 26 | Check that continue button is working or not | High | 1
Travels and Add-onns
Epic 5 | Story 1 | Check User is able to navigate to ancillary page. | High | 0.5 | Punita Jhamnani
| Story 2 | Check User is able to see the text "Review Your Booking" or not . | Medium | 0.5
| Story 3 | Check user is able to see Status Bar or not . | High | 0.5
| Story 4 | Check the Display of Meal Tab With its Object. | High | 1
| Story 5 | Check User is able to select "Non-Vegetarian Food Items"under Meal Tab with it's icon and amount. | High | 1
| Story 6 | Check User is able to select "Vegetarian Food Items"under Meal Tab with it's icon and amount. | High | 1
| Story 7 | Check User is able to add your preferred meal after clicking on the button "ADD". | High | 1
| Story 8 | Check the Display of Footer Section With its Object. | High | 1
| Story 9 | Check Reset Link is woking properly or not. | High | 1
| Story 10 | Check the Display of Baggage Tab With its Object. | High | 1
| Story 11 | Check user is able to select "Additional 5 Kg"option under Baggage Tab with its icon and amount. | High | 1
| Story 12 | Check user is able to select "Additional 10 Kg"option under Baggage Tab with its icon and amount. | High | 1
| Story 13 | Check are you able to add extra baggage option after clicking on the button "ADD". | High | 1
| Story 14 | Check the Display of Footer Section With its Object. | High | 1
| Story 15 | Check "Continue" Button is navigating you to the next Page or not. | High | 1
PAYMENT GATEWAY
Epic 6 | Story 1 | Check User is able to navigated on Payment Page. | High | 0.5 | Punita Jhamnani
| Story 2 | Check the "Simply Travel Wallet" text displayed on the top of the page or not. | Medium | 1
| Story 3 | Check the Details under "Simple Travel Wallet"text is displaying or not. | Medium | 1
| Story 4 | Check each and every Payment Option is working Properly or not under Payment Tab. | High | 1
| Story 5 | Check User is able to select option under "UPI" mode of Payment. | High | 1
| Story 6 | Check User is able to select option under "Net Banking" mode of Payment. | High | 1
| Story 7 | Check User is able to select Major bank under "Mobile Wallet" mode of Payment | High | 1
| Story 8 | Check User is able to select option under "No Cost EMI "mode of Payment. | High | 1
| Story 9 | Check User is able to select type of money under "Paypal" mode of Payment. | High | 1
| Story 10 | Check the "Finish Payment" Button functionality. | High | 0.5
BOOKING SUMMARY
Epic 7 | Story 1 | Check the Final details under Successfully Booked Ticket Tab that is comprises of Flight name,Duration of journey,Time of Flight amd Total price. | High | 1 | Punita Jhamnani
| Story 2 | Check the Book Summary Tab on the right hand side of the page. | High | 1
LOGOUT
Epic 8 | Story 1 | verify after successfull login click on profile icon to check logout button is visible or not. | High | 1 | Radha Panchal
| Story 2 | Verify logout option from by selecting 'Right coloumn option | low | 1
| Story 3 | Verify the session status, after logging and closing the browser without logging out | Medium | 2
| Story 4 | Verify logout option is not displayed under 'My Account'. | High | 1
| Story 5 | verify logout option is not displayed under 'Right Column' option before you login. | low | 1
| Story 6 | verify logout option is clickable or not | High | 1

## Test Scenerio
Module | Test Scenario
Registration | Check Signup button is displayed at https://examples.testsigma.com/
Check the user is able to navigate to the register page by clicking on Signup Button.
Check the header of the registration page and text "Register to travel account" is visible or not
Check all the Required fields by filling and not filling any data and Verify if blank spaces are passed in required fields.
Verify the numbers and special characters are not allowed in the Fullname fields.
Check that the user is able to register with all the valid and invalid email addresses.
Check that user is able to register with all the valid and invalid phone number
Verify user is able to select one of the Age group and Gender in radio button while registeration
Verify user is able to select Hobbies and Interests from the checkbox while registration
Check all the password validations with all different combinations.
Verify user has entered same password in both the password and confirm password section
Check the profile picture button is working or not and it should ask for the location for upload
Check is there any restriction of image file size to upload and the image are uploading or not
Verify the user is able to register by clicking on register button
Verify that the user is redirected to appropriate page after successful registeration
Login_Logout | Check the user is able to navigate to login page
verify if a user will be able to login with a valid username and valid password.
Verify if a user cannot login with a invalid username and an valid password.
verify the login functionality with valid username and invalid password.
verify the user login with blank username.
verify the user login with blank password.
verify the user is able to fill"password"in the textbox.
Verify if the data in password field is either visible as asterisk or bullet signs.
check the user is able to click on forget password navigate to the forget password.
verify if a user is able to login with a new password only after he/she has changed the password.
Verify if the ‘Login’ key of the keyboard is working correctly on the login page.
Verify if user enter invalid data then user is able to see error message
check the user is able to enter valid data & get successfull login.
verify after successfull login click on profile icon to check logout button is visible or not.
Verify logout option from by selecting 'Right coloumn option
Verify the session status, after logging and closing the browser without logging out
verify logout option is not displayed under 'My Account'.
verify logout option is not displayed under 'Right Column' option before you login.
verify logout option is clickable or not.
Search Flight | check the user is able to navigate through Go To Travel button.
check the user to display one way flying , round trip flying, multicity button.
check the user can navigate to one way flying , round trip flying, multicity page using button.
check are you able to city you are going to fly from and fly to.
check the departure button.
check you should enter the date of departing .
check number of passengers (adults ,children and infant) and it should not exceed 12 and then select class (Economicy ,Premium economy, Business, First Class) then press the done button.
check once you enter all the necessary information and press the Done button, you will be redirected to the page with search results. Here you can find recommended content that matches your criteria a diverse number of flights available.
Check from top you can apply the Sort and Filter functionality to find a flight based on your specific needs and requirements.
Check the filters are applied in real time that means you don’t need to press the Confirm button to see them applied. Sort and Filter functionality allows you to sort filters that you want to be applied. a. number of stops; b. airlines; c. lowest and highest price;
Check once you can press the Reset button to reset all the information selected in one click.
Check you have selected the flight, you can press the Apply button. Then you will be shown a range of airlines for returning flights to choose from.and redirected to the trip summary page.
Verify you can see information about the flight, see flight and baggage fee details, change flights if it is necessary and then continue the Booking process.
Review your booking | Check the book now button is working or not
check the itienary text is visible or not
check the flight details is visible or not
check the arrival and departure details is available or not
Check that baggage details is visible or not below flight details
check the fare summary tab with all details is displaying correctly or not
Check the cancellation and data change is visible or not
Check that in know more information is visible or not
Check that coupon code is entering correct or not
Check that baggage under important information is visible or not
Check that Adds ons text is visible or not below the important information
Check that all benefits are under the Adds on tab
Check that select yes for conform the trip button is selected or not
Check that button thanks for donating is selected or not
Check that continue button is working or not
Check that flight summary text is visible or not
Check that flight details link is working or not
Check that traveller details text is visible or not
Check that Add adults functionalities working or not
Check the first name and last name is taking the text or not
Check the male or female by clicking the radio button is working or not
Check that contact information is visible or not
Check that mobile number and email id entering correct or not
Check that GST number of business travel is visible or not
Check the acknowledgment check box is working or not
Check that continue button is working or not
Travels and Add-Onns | Check User is able to navigate to ancillary page
Check User is able to see text and status bar under Header Section
Check User is able to click on Meal Tab and its object .
Check User is able to select Vegitarian and Non-Vegitarian Food Items
Check User is able to see total amount as per the food he/she selected
Check User is able to select Reset link in footer section
Check User is Able to click on Continue Botton.
Check User is able to click on the Baggage tab and its object.
Check User is able to select option from a Baggage tab.
Check User is able to see the total amount as per baggage he/she is selected
Check User is able to click on the Continue Button.
Payment Gateway | Check User is able to navigate to the Payment page.
Check User is able to see the text under the Header section.
Check User is able to see the object under the text"Simple Travel Wallet".
Check user is able to see the Payment Tab and its Option.
Check User is able to Select UPI Payment option.
Check User is able to select "Net Banking"Payment option.
Check User is able to Select"No Cost EMI"Payment option.
Check User is able to selecy "Paypal"Payment option.
Check User is able to click on the "Finish Payment " Button
Booking Summary | Check User is able to see the the Booking Summary of the flight.
Check User is able to see the final details of the flight.

## Registration
|  |  | Module Name | Registration
|  |  | Done By | Reshma K.R
REGISTRATION MODULE
User Story | Functionalities | Test Case ID | Test Case Name | Pre-Requisities | Test Case Steps | Test Data | Expected Result | Actual Result | Status | Additional Comments | Tester
1 | Check Signup button is displayed at https://examples.testsigma.com/ | TC_Reg_01 | Check display of Signup button | NA | 1.Launch the browser. | Goto URL https://examples.testsigma.com/ | Signup buttton should be displayed at https://examples.testsigma.com/ |  | Pass
2 | Check the user is able to navigate to the register page by clicking on Signup button | TC_Reg_02 | Validate the Navigation for registration page | Navigate to homepage page from any browser using below url: https://examples.testsigma.com/ | 1. Launch the Browser. 2. Click on the Signup button on homepage. | Goto Register URL https://travel.testsigma.com/signup | Should be navigate on registration page after clicking on Signup button. |  | Pass
3 | Check the header of the registration page | TC_Reg_03 | Display the header of registration page | 1.Navigate to homepage page from any browser using below url: https://examples.testsigma.com/ 2.Click on Signup button | 1. Launch the browser. 2. Navigate to register page by clicking Signup button. 3. Verifying the logo. 4. Verifying the display of header | Goto Register URL https://travel.testsigma.com/signup | All header should display after navigating to register page by clicking on the Signup button. |  | Pass
4 | Check user is able to see "Register to travel account" line | TC_Reg_04 | Display the text/line | 1.Navigate to homepage page from any browser using below url: https://examples.testsigma.com/ 2.Click on Signup button | 1. Launch the browser. 2. Navigate to register page by clicking Signup button. 3. Verifying the display of text/line | Goto Register URL https://travel.testsigma.com/signup | Should display "Register to travel account" text/line |  | Pass
5 | Check all the Required fields by filling and not filling any data and Verify if blank spaces are passed in required fields. | TC_Reg_05 | Check user should Register by filling all the required fields | Navigate to registration page https://travel.testsigma.com/signup | 1. Enter valid data in the all the required fields. 2. Click on the Register button. | 1. Fullname: Reshma Kalapurackal 2. Email: reshma@gmail.com 3.Phone: 5148323985 4.Address: D303 xyz bldg 5.Password: Sample@123 5. Re-enter Password: Sample@123 | User should be registered successful by filling all required fields. |  | Pass
|  | TC_Reg_06 | Check the required fields by not filling any data | Navigate to registration page https://travel.testsigma.com/signup | 1. Do not fill any data in required fields.. 2. Click on the Register button. | 1. Fullname: 2. Email: 3.Phone: 4.Address: 5.Password: 5. Re-enter Password: | Should display validation message and display mandatory symbol on all required fields. |  | Pass
|  | TC_Reg_07 | Blank spaces in required fields | Navigate to registration page https://travel.testsigma.com/signup | 1. Passed blank spaces in all required fields. 2. Click on the Register button |  | Should display Validation error message for all required fields. | Not displaying any error message like - Blank space not valid | Fail
6 | Verify the numbers and special characters are not allowed in the Fullname fields. | TC_Reg_08 | Verify by entering number in the Fullname field | Navigate to registration page https://travel.testsigma.com/signup | 1. Enter number in the Fullname field 2.Click on the register button | 1.Fullname: 2563 | Should display Validation error message in Fullname field. | Not displaying any error message like- numbers not allowed | Fail
|  | TC_Reg_09 | Verify by entering special character in the Fullname field |  | 1.Enter special character in the Fullname fiels | 1.Fullname: @# | Should display Validation error message in Fullname field. | Not displaying any error message like- Special characters are not allowed | Fail
7 | Check that the user is able to register with all the valid and invalid email addresses. | TC_Reg_10 | Verify the system is accepting all the valid email address or not. | Navigate to registration page https://travel.testsigma.com/signup | 1. Launch the browser. 2. Navigate to register page by clicking Signup button. 3. Enter valid email address in email field. 4. Enter valid data in required fields. 5. Click on the Register button | 1. Email: sample123@gmail.com 2. Email: sample@gmail.com | Should not display any validation message or error in valid email field. |  | Pass
|  | TC_Reg_11 | Validate for some invalid emails with cases like: without @, without(.), without domain, without alphabets before @. | Navigate to registration page https://travel.testsigma.com/signup | 1. Enter invalid email 2. Enter valid data in rest of the required fields 3. Click on the Register button | 1. Email: samplegmail.com 2. Email: sample@gmailcom 3. Email: samplegmail.com 4. Email: @gmail.com | Should display validation message for invalid email address and the user should not be able to register. | not displaying error message when .com is not added in mail id | Fail
|  | TC_Reg_12 | Verify user should not be able to registered with valid but duplicate/ already existing email address. | Navigate to registration page https://travel.testsigma.com/signup | 1. Enter already registered email address 2. Enter valid data in rest of the required fields 3. Click on the Register button | 1.Email: sample123@gmail.com | Should not be able to register with existing email and ask to login instead and should display validation message like - The specified email already exists. | Already registered email id are getting accepted | Fail
8 | Check that user is able to register with all the valid and invalid phone number | TC_Reg_13 | Verify the system is accepting all the valid phone number or not. | Navigate to registration page https://travel.testsigma.com/signup 1.Enter the Fullname 2.Enter the email address | 1.Launch the browser 2.Navigate to register page by clicking Signup button 3.Enter valid phone number 4.Enter valid data in rest of the required field 5.Click on register button | 1.Phone: 1234567899 | Should not display any validation message or error in valid phone number field. |  | Pass
|  | TC_Reg_14 | Validate for some invalid phone number with cases like: with special character or with alphabets |  | 1. Enter invalid phone number 2. Enter valid data in rest of the required fields 3. Click on the Register button | 1.Phone: 1234@#6789 2.Phone: 123a4b5et3 | Should display validation message for invalid phone number and user should not be able to register. | Special character and alphabets are accepted while registering in phone number field | Fail
|  | TC_Reg_15 | Verify user should not be able to registered with valid but duplicate/ already existing phone number. |  | 1. Enter already registered phone number 2. Enter valid data in rest of the required fields 3. Click on the Register button | NA | Should not be able to register with existing phone number and ask to login instead or enter different phone number and should display validation message like - The specified phone number already exists. | already registered phone number are able to register | Fail
9 | Verify user is able to select one of the Age group in radio button while registeration | TC_Reg_16 | Validate radio button for Age group fields | 1. Navigate to registration page 2.Enter valid data in required fields. | 1. Select age group by clicking on radio button 2. Click on the Register button | Age group: 1. Below 25 2. 26 to 55 3. Above 55 | Should be able to select/choose one value by clicking on radio button. |  | Pass
10 | Verify user is able to select one of the gender in radio button while registeration | TC_Reg_17 | Validate radio button for Gender fields | 1. Navigate to registration page 2.Enter valid data in required fields. | 1. Select gender by clicking on radio button 2. Click on the Register button | Gender: 1. Male 2. Female 3. Other | Should be able to select/choose one value by clicking on radio button. |  | Pass
11 | Verify user is able to select Hobbies from the checkbox while registration | TC_Reg_18 | Validate checkbox button for hobbies fields | 1. Navigate to registration page 2.Enter valid data in required fields. | 1. Select hobbies by clicking on checkbox 2. Click on the Register button | Hobbies: 1. Cricket 2. Movies 3. Hockey | Should be able to select/choose value by clicking on checkbox button. |  | Pass
12 | Verify user is able to select Interests from the checkbox while registration | TC_Reg_19 | Validate checkbox button for Interests fields | 1. Navigate to registration page 2.Enter valid data in required fields. | 1. Select interests by clicking on checkbox 2. Click on the Register button | Interests: 1. Job 2. Business 3. Agriculture | Should be able to select/choose value by clicking on checkbox button. |  | Pass
13 | Check all the password validations with all different combinations. | TC_Reg_20 | Verify that password fields should be encrypted with * symbol while entering password and confirm password. | 1.Navigate to registration page https://travel.testsigma.com/signup 2. Enter valid data in required fields | 1. Enter valid data in required fields 2.Enter a password 2. Enter a confirm password | 1. Password: 123456 2. Confirm Password: 123456 | Should display * symbol while entering password. |  | Pass
|  | TC_Reg_21 | Validate the password value not be less than 6 characters. |  | 1. Enter valid data in required fields 2.Enter a password with less than 6 characters. | 1. Password: Test1 2. Confirm Password: Test1 | Should be prompt the user - The password should have at least 6 characters. | Password less than 6 character are getting accepted | Fail
|  | TC_Reg_22 | Validate the password value not be greater than 16 characters. |  | 1. Enter valid data in required fields 2. Enter a password with more than 16 characters. | 1. Password: Samplepass0112345 2. Confirm Password: Samplepass0112345 | It should prompt the user to enter a value between 6 to 16 characters | Password more than 16 character are getting accepted | Fail
|  | TC_Reg_23 | Verify the password should contains a special characters, lowercase, uppercase and numbers. |  | 1. Enter valid data in required fields 2. Enter a password with valid rules | 1. Password: Sample@123 2. Confirm Password: Sample@123 | Should be able to register with any minimum 6 characters or more than 6 character. |  | Pass
14 | Verify user has entered same password in both the password and confirm password section | TC_Reg_24 | Verify if the Password and Confirm Password fields are accepting similar values only. | 1.Navigate to registration page https://travel.testsigma.com/signup 2. Enter valid data in required fields | 1. Enter a password 2. Enter a confirm password with same password value | 1. Password: Sample@123 2. Confirm Password: Sample@123 | Should not display any validation message if password and confirm password match. |  | Pass
|  | TC_Reg_25 | Verify that user should get validation error message when enter mismatch values in both password and confirm password fields. |  | 1. Enter a password 2. Enter a confirm password with different value | 1. Password: Sample@123 2. Confirm Password: 123456 | Should display validation message if password and confirm password do not match. | Not displaying error message when different password are entered in password and confirm password | Fail
15 | Check the profile picture button is working or not | TC_Reg_26 | Validate profile picture buttion is workable | 1.Navigate to registration page https://travel.testsigma.com/signup 2. Enter valid data in required fields | 1.Click on profile picture button | NA | Profile picture button should be working |  | Pass
16 | Check on the click upload button it should ask for the location to upload | TC_Reg_27 | Validate the navigation to location page to upload | 1.Navigate to registration page https://travel.testsigma.com/signup 2. Enter valid data in required fields | 1.Click on profile picture button 2.Navigate to location for upload | NA | Should be able to navigate to location for upload |  | Pass
17 | Check is there any restriction of image file size to upload | TC_Reg_28 | Verify the image selected is within the restricted size | 1.Navigate to registration page https://travel.testsigma.com/signup 2. Enter valid data in required fields | 1. Click on profile picture 2. Navigate to location for upload 3.Select the restricted size picture to upload | NA | Should be able to upload the profile picture |  | Pass
|  | TC_Reg_29 | Verify the image selected is not within the restricted size |  | 1. Click on profile picture 2. Navigate to location for upload 3.Select the non restricted size picture to upload | NA | Should display validation error /message - Image size exceeded | Not displaying Image size exceeded error message | Fail
18 | Check whether the image are uploading or not | TC_Reg_30 | Verify images are uploaded in the input field | 1.Navigate to registration page https://travel.testsigma.com/signup 2. Enter valid data in required fields | 1.Click on profile picture 2.navigate to loaction for upload 3.Select the picture to upload 4.Click on upload 5.Click on register button | NA | Should be able to upload the profile picture in the input field |  | Pass
|  | TC_Reg_31 | Verify images are uploaded in the profile section | 1.Navigate to registration page https://travel.testsigma.com/signup 2. Enter valid data in required fields 3.Upload picture 4.Click on register | 1.Click on profile picture 2.navigate to loaction for upload 3.Select the picture to upload 4.Click on upload 5.Click on register button 6.Click on profile picture | NA | Should display the picture in profile section. | Uploaded picture is not able to see in profile section | Fail
19 | Verify the user is able to register by clicking on register button | TC_Reg_32 | Validate Register button | 1.Navigate to registration page https://travel.testsigma.com/signup 2. Enter valid data in required fields | 1. Launch the browser. 2. Navigate to register page by clicking Signup button. 3. Enter valid data in the required fields. 4. Click on the Register button. | 1. Fullname: Reshma Kalapurackal 2. Email: reshma@gmail.com 3.Phone: 5148323985 4.Address: D303 xyz bldg 5.Password: Sample@123 5. Re-enter Password: Sample@123 | Should be able to registered successful and navigate to the registered complete page. |  | Pass
20 | Verify that the user is redirected to appropriate page after successful registeration | TC_Reg_33 | Navigate to appropriate page after successful register. | 1.Navigate to registration page https://travel.testsigma.com/signup 2. Enter valid data in required fields | 1. Launch the browser. 2. Navigate to register page by clicking Signup button. 3. Enter valid data in the required fields. 4. Click on the Register button. | NA | Should be able to navigate to "https://travel.testsigma.com/" after successful register |  | Pass

## Login
|  |  |  | Module Name | LOGIN
|  |  |  | Done By | Radha Panchal
LOGIN
User story | Functionalities | Test Case Id | Test Case Name | Pre-Requisties | Test case steps | Test Data | Expected Results | Actual Results | Status | Additional comment | Tester
1. | Check the user is able to navigate to login page | TC_Log_001 | Display of the Login page | User should have Login Credential | 1.Open browser 2.go to url :https://examples.testsigma.com/ 3.click on login from the homepage | N/A | The user is successfully able to navigate login page. |  | Pass
2. | verify if a user will be able to login with a valid username and valid password. | TC_Log2 | check User is able to login valid username and password or not | 1.Open browser 2.go to url :https://examples.testsigma.com/ 3.click on login from the homepage | 1.Enter valid Username 2.Enter valid password 3.click on login button | 1.rp@gmail.com 2."123@123*" | The user should be able to login 1.Valid Email Id 2.Valid Password | when i enter valid username and valid password not able to login. | Fail
3 | Verify the Login functionality with invalid username and an valid password. | TC_log003 0 | check User is unable to login with invalid email and valid password | 1.Open browser 2.go to url :https://examples.testsigma.com/ 3.click on login from the homepage 4.Enter valid username and password | 1.Enter valid Username 2.Enter valid password 3.click on login button | 1.radhapanchal 2.******** | Message should be displayed in red color as "please enter valid username and Password. |  | Pass
4 | Verify the Login functionality with valid username and an invalid password. | TC_Log004 | check user is able to Login with valid username and invalid password | 1.Open browser 2.go to url :https://examples.testsigma.com/ 3.click on login from the homepage 4.Enter valid username and password | 1.Enter valid Username 2.Enter valid password 3.click on login button | 1.Rp@gmail.com 2.*81 | Message should be displayed in red color as Wrong password |  | Pass
5 | Verify the user is login with blank username | TC_Log005 | check user is able to login with blank username. | 1.Open browser 2.go to url :https://examples.testsigma.com/ 3.click on login from the homepage 4.Enter valid username and password | 1.Enter valid Username 2.Enter valid password 3.click on login button | N/A | Message should be displayed in red color as wrong username |  | Pass
6 | verify the user is able to login with blank password | TC_Log4 | check User is unable to login with blank password. | 1.Open browser 2.go to url :https://examples.testsigma.com/ 3.click on login from the homepage 4.Enter valid username and password | 1.Enter valid Username 2.Enter valid password 3.click on login button | 1.radhapanchal 2. | Message should be displayed in red color as "Blank username not allowed please enter valid username | not diplaying error message as blank username is not allowed Please enter valid username | Fail
7 | verify the user is able to fill "password"in the textbox. | TC_Log5 | check the user is taken to login with valid password | 1.Open browser 2.go to url :https://examples.testsigma.com/ 3.click on login from the homepage 4.Enter valid username and password | 1.Enter valid Username 2.Enter valid password 3.click on login button | 1.radhapanchal 2.Radha1234* | user after entered password is displayed successfully. |  | Pass
8 | Verify if the data in password field is either visible as asterisk or bullet signs | TC_Log6 | check if user is display password field is visible as asterisk or not | 1.Open browser 2.go to url :https://examples.testsigma.com/ 3.click on login from the homepage 4.Enter valid username and password | 1.Enter valid Username 2.Enter valid password 3.click on login button | 1.radhapanchal 2.Radha1234* | User should be login with special character |  | Pass
9 | check the user is able to navigate forget password option | TC_Log7 | check user is able to navigate forgot password option | 1.Open browser 2.go to url :https://examples.testsigma.com/ 3.click on login from the homepage 4.Enter valid username and password | Click on forgot Password Link | N/A | user should be able to navigate forgot password option |  | Pass
10 | verify if a user is able to login with a new password only after he/she has changed the password. | Tc_Log9 | check user Is able to login with new password or not | 1.Open browser 2.go to url :https://examples.testsigma.com/ 3.click on login from the homepage 4.Enter valid username and password | 1.Enter valid Username 2.Enter valid password 3.click on login button | 1.radhapanchal 2.******** | user should be able to login new password. | not able to login with new password | Fail
11 | Verify if the ‘Login’ key of the keyboard is working correctly on the login page. | Tc_Log10 | check the' Login' key of the keyboard is working or not | 1.Open browser 2.go to url :https://examples.testsigma.com/ 3.click on login from the homepage 4.Enter valid username and password | Click on Enter Key button on your Keyboard | N/A | If 'Login ' key is working properly user is able to login successfully. |  | Pass
12 | Verify if user enter invalid data then user is able to see error message | TC_Log12 | check user is Enter to login valid username and invalid password error message displayed ot not | 1.Open browser 2.go to url :https://examples.testsigma.com/ 3.click on login from the homepage 4.Enter valid username and password | 1.Enter valid Username 2.Enter invalid password 3.click on login button | N/A | user should not be able to login invalid data. |  | Pass
13 | Verify the user is able to enter valid data & get successfull login. | TC_Log13 | check user is able to login valid username and valid password | 1.Open browser 2.go to url :https://examples.testsigma.com/ 3.click on login from the homepage 4.Enter valid username and password | 1.Enter valid Username 2.Enter valid password 3.click on login button | 1.radhapanchal 2.Radha1234* | user is able login successfully. | It displaying error message when i enter valid username and password as a user i am not able to Login successfully. | Fail

## Search Flight
|  |  | Module Name | SEARCH/FILTER ITEM
|  |  | Done By | Ruchita Sapkal
SEARCH/FILTER ITEMS
Test Case ID | User Story | Functionalities | Test Case Name | Pre-Requisities | Test Case Steps | Test Data | Expected Result | Actual Result | Status | Additional Comments | Tester
TC ET 01 | 1 | check the user is able to navigate through Go To Travel button. | Validate Search Go To Travel button is clickable | Navigate to homepage page from any browser using below url: https://examples.testsigma.com/ | 1.Navigate to homepage page. 2. Click on the Go To Travel Button. | NA | User should navigate to travel page"https://travel.testsigma.com/". |  | Pass
TC ET 02 | 2 | check the user to display one way flying , round trip flying, multicity button. | Verify display one way flying , round trip flying, multicity button.. | Navigate to Go To Travel page. https://examples.testsigma.com/ | Verify the display of type of flight journey. | NA | The following object will display:- 1.One-Way Flying 2.Round Trip Flying 3.Multi City |  | Pass
TC ET 03 | 3 | check the user can navigate to one way flying page using button. | Verify display of search one way flying page | Navigate to Go To Travel page. https://examples.testsigma.com/ | 1. Navigate to Go To Travel page.. 2. Click on the one way flying button. | NA | Should navigat to One flying page |  | Pass
TC ET 04 | 4 | check are you able to city you are going to fly from and fly to. | Validate user navigating correct going to fly from and fly to search. | Navigate to one way flying page. https://examples.testsigma.com/ | 1. Navigate to one way flying page. 2. Enter city you are going to fly from and fly to value in search box. | NA | User should redirect respectivegoing to fly from and fly to value . |  | Pass
TC ET 05 | 5 | check the departure button. | Validate user departure button is clickable. | Navigate to one way flying page. https://examples.testsigma.com/ | 1. Navigate to one way flying page. 2. Click on the Departure button. | NA | Button is Clickable |  | Pass
TC ET 06 | 6 | check you should enter the date of departing . | Validate search date of departing. | Navigate to one way flying page. https://examples.testsigma.com/ | 1. Navigate to one way flying page.. 2. Enter the date of departing. | NA | Should Display the date calender. |  | Pass
TC ET 07 | 7 | check number of passengers (adults ,children and infant) and it should not exceed 12 and then select class (Economicy ,Premium economy, Business, First Class) then press the done button. | Validate all items details should be visible. | Navigate to one way flying page. https://examples.testsigma.com/ | 1.Navigate to one way flying page. 2. number of passengers (adults ,children and infant) and it should not exceed 12 and then select class (Economicy ,Premium economy, Business, First Class) then press the done button. | NA | Should Display the following objects:- 1.No of Adults. 2.No of children 3.No of infants. 4.Travel class 5.Display the Done Button. |  | Pass
TC ET 08 | 8 | check once you enter all the necessary information and press the Done button, you will be redirected to the page with search results. Here you can find recommended content that matches your criteria a diverse number of flights available. | Validate all items details should be visible. | Navigate to one way flying page. https://examples.testsigma.com/ | 1. Navigate to one way flying page. 2. Click on that search button. | NA | flight details should be visible for all search items. | fail all items details should be visible. | fail
TC ET 09 | 9 | Check from top you can apply the Sort and Filter functionality to find a flight based on your specific needs and requirements. | Validate search filter visible. | Navigate to one way flying page. https://examples.testsigma.com/ | 1. Navigate to one way flying page. 3. Enter search value in search box that is available in database. 4. Go to the Search Filter 5. Select/click on the checkbox. | NA | All fields should be visible after clicking on checkbox. | Fail search filter visible. | fail
TC ET10 | 10 | Check the filters are applied in real time that means you don’t need to press the Confirm button to see them applied. Sort and Filter functionality allows you to sort filters that you want to be applied. a. number of stops; b. airlines; c. lowest and highest price; | Validate advanced search filter by various categories. | Navigate to one way flying page. https://examples.testsigma.com/ | 1. Navigate to one way flying page. 2. Enter search value in search box that is available in database. 3. Go to the Advanced Search Filter 4. Select any dropdown value in functionality and apply other filter as well. 5. Click on the Search button. | NA | Should be able to filter by various flight details | Fail advanced search filter by various categories. | fail
TC ET 11 | 11 | Check once you can press the Reset button to reset all the information selected in one click. | Verify reset button is clickable . | Navigate to one way flying page. https://examples.testsigma.com/ | 1. Navigate to one way flying page.. 2. Enter search value in search box that available in database. 4. Go to the Search Filter. 5. Apply filter. 6. Click on the reset button. | NA | Reset Button is clickable | Fail reset button is clickable . | fail
TC ET 12 | 12 | Check you have selected the flight, you can press the Apply button. Then you will be shown a range of airlines for returning flights to choose from.and redirected to the trip summary page. | Validate flight details | Navigate to one way flying page. https://examples.testsigma.com/ | 1. Navigate to one way flying page.. 2. Enter search value in search box that available in database. 4. Go to the Search Filter. 5. Apply filter. 6. display valid flight details. | NA | display valid flight details |  | Pass
TC ET 13 | 13 | Verify you can see information about the flight, see flight and baggage fee details, change flights if it is necessary and then continue the Booking process. | Validate see information about the flight, see flight and baggage fee details, change flights. | Navigate to one way flying page. https://examples.testsigma.com/ | 1. Navigate to one way flying page.. 2. Enter search value in search box that available in database. 4. Go to the Search Filter. 5. Apply filter. 6. display valid information about the flight, see flight and baggage fee details, change flights details. | NA | display valid information about the flight, see flight and baggage fee details, change flights details. |  | Pass
TC ET 14 | 14 | check the user can navigate to Round Trip Flying page using button. | Check Round Trip Flying is clickable. | Navigate to homepage page. https://examples.testsigma.com/ | 1.Navigate to homepage page. 2. Click on the Go To Travel Button. | NA | Travel Button is Clickable |  | Pass
TC ET 15 | 15 | check the user can navigate to Round Trip Flying page using button. | Verify display of search to Round Trip Flying page | Navigate to Round Trip Flying https://examples.testsigma.com/ | 1. Navigate to Round Trip Flying. 2. Click on the one way flying button. | NA | should display search result page. |  | Pass
TC ET 16 | 16 | check are you able to city you are going to fly from and fly to. | Validate user navigating correct going to fly from and fly to search. | Navigate to Round Trip Flying https://examples.testsigma.com/ | 1. Navigate to Round Trip Flying. 2. Enter city you are going to fly from and fly to value in search box. | NA | Should display search result page. |  | Pass
TC ET 17 | 17 | check the departure button. | Validate user departure button is clickable. | Navigate to Round Trip Flying https://examples.testsigma.com/ | 1. Navigate to Round Trip Flying. 2. Click on the Departure button. | NA | check Departure button is clickable |  | Pass
TC ET 18 | 18 | check you should enter the date of departing . | Validate search date of departing. | Navigate to Round Trip Flying https://examples.testsigma.com/ | 1. Navigate to Round Trip Flying. 2. Enter the date of departing. | NA | Should Display the date calender. |  | Pass
TC ET 19 | 19 | check number of passengers (adults ,children and infant) and it should not exceed 12 and then select class (Economicy ,Premium economy, Business, First Class) then press the done button. | Validate all items details should be visible. | Navigate to Round Trip Flying https://examples.testsigma.com/ | 1. Navigate to Round Trip Flying. 2. number of passengers (adults ,children and infant) and it should not exceed 12 and then select class (Economicy ,Premium economy, Business, First Class) then press the done button. | NA | Should be get proper validation flight match in search iteam. |  | Pass
TC ET 20 | 20 | check once you enter all the necessary information and press the Done button, you will be redirected to the page with search results. Here you can find recommended content that matches your criteria a diverse number of flights available. | Validate all items details should be visible. | Navigate to Round Trip Flying https://examples.testsigma.com/ | 1. Navigate to Round Trip Flying. 2. Click on that search button. | NA | Should be get proper validation flight match in search | fail all items details should be visible. | fail
TC ET 21 | 21 | Check from top you can apply the Sort and Filter functionality to find a flight based on your specific needs and requirements. | Validate search filter visible. | Navigate to Round Trip Flying https://examples.testsigma.com/ | 1. Navigate to Round Trip Flying. 3. Enter search value in search box that is available in database. 4. Go to the Search Filter 5. Select/click on the checkbox. | NA | display valid flight details | Fail search filter visible. | fail
TC ET 22 | 22 | Check the filters are applied in real time that means you don’t need to press the Confirm button to see them applied. Sort and Filter functionality allows you to sort filters that you want to be applied. a. number of stops; b. airlines; c. lowest and highest price; | Validate advanced search filter by various categories. | Navigate to Round Trip Flying https://examples.testsigma.com/ | 1. Navigate to Round Trip Flying. 2. Enter search value in search box that is available in database. 3. Go to the Advanced Search Filter 4. Select any dropdown value in functionality and apply other filter as well. 5. Click on the Search button. | NA | display valid information about the flight, see flight and baggage fee details, change flights details. | Fail advanced search filter by various categories. | fail
TC ET 23 | 23 | Check once you can press the Reset button to reset all the information selected in one click. | Verify reset button is clickable . | Navigate to Round Trip Flying https://examples.testsigma.com/ | 1. Navigate to Round Trip Flying. 2. Enter search value in search box that available in database. 4. Go to the Search Filter. 5. Apply filter. 6. Click on the reset button. | NA | User should get the correct result after clicking on search button. | Fail reset button is clickable . | fail
TC ET 24 | 24 | Check you have selected the flight, you can press the Apply button. Then you will be shown a range of airlines for returning flights to choose from.and redirected to the trip summary page. | Validate flight details | Navigate to Round Trip Flying http://demowebshop.tricentis.com | 1. Navigate to Round Trip Flying. 2. Enter search value in search box that available in database. 4. Go to the Search Filter. 5. Apply filter. 6. display valid flight details. | NA | display valid flight details |  | Pass
TC ET 25 | 25 | Verify you can see information about the flight, see flight and baggage fee details, change flights if it is necessary and then continue the Booking process. | Validate see information about the flight, see flight and baggage fee details, change flights. | Navigate to Round Trip Flying https://examples.testsigma.com/ | 1. Navigate to Round Trip Flying. 2. Enter search value in search box that available in database. 4. Go to the Search Filter. 5. Apply filter. 6. display valid information about the flight, see flight and baggage fee details, change flights details. | NA | display valid information about the flight, see flight and baggage fee details, change flights details. |  | Pass
TC ET 26 | 26 | check the user can navigate to Multicity Flying page using button. | Check Multicity Flying is clickable. | Navigate to homepage page. https://examples.testsigma.com/ | 1.Navigate to homepage page. 2. Click on the Multicity Travel Button. | NA | check Multicity button is clickable |  | Pass
TC ET 27 | 27 | check the user can navigate to Multicity Flying page using button. | Verify display of search to Multicity Flying page | Navigate to Multicity Flying https://examples.testsigma.com/ | 1. Navigate to Multicity Flying. 2. Click on the one way flying button. | NA | should display search result page. |  | Pass
TC ET 28 | 28 | check are you able to city you are going to fly from and fly to. | Validate user navigating correct going to fly from and fly to search. | Navigate to Multicity Flying https://examples.testsigma.com/ | 1. Navigate to Multicity Flying. 2. Enter city you are going to fly from and fly to value in search box. | NA | Should display search result page. |  | Pass
TC ET 29 | 29 | check the departure button. | Validate user departure button is clickable. | Navigate to Multicity Flying https://examples.testsigma.com/ | 1. Navigate to Multicity Flying. 2. Click on the Departure button. | NA | check Departure button is clickable |  | Pass
TC ET 30 | 30 | check you should enter the date of departing . | Validate search date of departing. | Navigate to Multicity Flying https://examples.testsigma.com/ | 1. Navigate to Multicity Flying. 2. Enter the date of departing. | NA | check Departure date is valid |  | Pass
TC ET 31 | 31 | check number of passengers (adults ,children and infant) and it should not exceed 12 and then select class (Economicy ,Premium economy, Business, First Class) then press the done button. | Validate all items details should be visible. | Navigate to Multicity Flying https://examples.testsigma.com/ | 1. Navigate to Multicity Flying. 2. number of passengers (adults ,children and infant) and it should not exceed 12 and then select class (Economicy ,Premium economy, Business, First Class) then press the done button. | NA | Should be get proper validation flight match in search iteam. |  | Pass
TC ET 32 | 32 | check once you enter all the necessary information and press the Done button, you will be redirected to the page with search results. Here you can find recommended content that matches your criteria a diverse number of flights available. | Validate all items details should be visible. | Navigate to Multicity Flying https://examples.testsigma.com/ | 1. Navigate to Multicity Flying. 2. Click on that search button. | NA | Should be get proper validation flight match in search | fail all items details should be visible. | fail
TC ET 33 | 33 | Check from top you can apply the Sort and Filter functionality to find a flight based on your specific needs and requirements. | Validate search filter visible. | Navigate to Multicity Flying https://examples.testsigma.com/ | 1. Navigate to Multicity Flying. 3. Enter search value in search box that is available in database. 4. Go to the Search Filter 5. Select/click on the checkbox. | NA | display valid flight details | Fail search filter visible. | fail
TC ET 34 | 34 | Check the filters are applied in real time that means you don’t need to press the Confirm button to see them applied. Sort and Filter functionality allows you to sort filters that you want to be applied. a. number of stops; b. airlines; c. lowest and highest price; | Validate advanced search filter by various categories. | Navigate to Multicity Flying https://examples.testsigma.com/ | 1. Navigate to Multicity Flying. 2. Enter search value in search box that is available in database. 3. Go to the Advanced Search Filter 4. Select any dropdown value in functionality and apply other filter as well. 5. Click on the Search button. | NA | display valid information about the flight, see flight and baggage fee details, change flights details. | Fail advanced search filter by various categories. | fail
TC ET 35 | 35 | Check once you can press the Reset button to reset all the information selected in one click. | Verify reset button is clickable . | Navigate to Multicity Flying https://examples.testsigma.com/ | 1. Navigate to Multicity Flying. 2. Enter search value in search box that available in database. 4. Go to the Search Filter. 5. Apply filter. 6. Click on the reset button. | NA | User should get the correct result after clicking on search button. | Fail reset button is clickable . | fail
TC ET 36 | 36 | Check you have selected the flight, you can press the Apply button. Then you will be shown a range of airlines for returning flights to choose from.and redirected to the trip summary page. | Validate flight details | Navigate to Multicity Flying https://examples.testsigma.com/ | 1. Navigate to Multicity Flying. 2. Enter search value in search box that available in database. 4. Go to the Search Filter. 5. Apply filter. 6. display valid flight details. | NA | display valid flight details |  | pass
TC ET 37 | 37 | Verify you can see information about the flight, see flight and baggage fee details, change flights if it is necessary and then continue the Booking process. | Validate see information about the flight, see flight and baggage fee details, change flights. | Navigate to Multicity Flying https://examples.testsigma.com/ | 1. Navigate to Multicity Flying. 2. Enter search value in search box that available in database. 4. Go to the Search Filter. 5. Apply filter. 6. display valid information about the flight, see flight and baggage fee details, change flights details. | NA | display valid information about the flight, flight detils and baggage fee details, change flights details. |  | pass

## Review Booking
|  |  |  | Module Name | Review your Booking
|  |  |  | Done By | Sai prathibha chenchireddy
Review your Booking
User Story | Functionalities | Test Case ID | Test Case Name | Pre-Requisities | Test Case Steps | Test Data | Expected Result | Actual Result | Status | Additional Comments | Tester
1 | Check the book now button functionality | TC ET 01 | Check User is able to book a flight after clicking book now from predefined flights. | 1.enter the url in the browser 2.https://examples.testsigma.com. 3.select the flight . | 1.Click on book now Button. | NA | The user should navigate to review page. |  | Pass
|  | TC ET 02 | Check User is able to book a flight after searching for particular flight detail. | 1.enter the url in the browser 2.https://examples.testsigma.com. 3.select the flight . | 1.Click on book now Button. | NA | The user should navigate to review page. |  | Pass
|  | TC ET 03 | Check User is able to book a flight after selecting one adult and one child. | 1.enter the url in the browser 2.https://examples.testsigma.com. 3.select the flight . | 1.Click on book now Button. | NA | The user should navigate to review page. |  | Pass
|  | TC ET 04 | Check User is able to book a flight after selecting one adult and more than 1 child. | 1.enter the url in the browser 2.https://examples.testsigma.com. 3.select the flight . | 1.Click on book now Button. | NA | The user should navigate to review page. |  | Pass
|  | TC ET 05 | Check User is able to book a flight after selecting one child and more than 1 adult. | 1.enter the url in the browser 2.https://examples.testsigma.com. 3.select the flight . | 1.Click on book now Button. | NA | The user should navigate to review page. |  | Pass
|  | TC ET 06 | check the user is able to book a flight afrer selecting more than 12 persons | 1.enter the url in the browser 2.https://examples.testsigma.com. 3.select the flight . | 1.Click on book now Button. | NA | The user should navigate to review page. | Total guest count cannot exceed 12 | Fail
|  | TC ET 07 | Check User is able to book a flight after selecting departure place. | 1.enter the url in the browser 2.https://examples.testsigma.com. 3.select the flight . | 1.Click on book now Button. | NA | The user should navigate to review page. |  | Pass
|  | TC ET 08 | Check User is able to book a flight after selecting place from where to fly. | 1.enter the url in the browser 2.https://examples.testsigma.com. 3.select the flight . | 1.Click on book now Button. | NA | The user should navigate to review page. |  | Pass
|  | TC ET 09 | Check User is able to book a flight after selecting departuring and current place. | 1.enter the url in the browser 2.https://examples.testsigma.com. 3.select the flight . | 1.Click on book now Button. | NA | The user should navigate to review page. |  | Pass
|  | TC ET 10 | Check User is able to book a flight after booking for a paticular date in one way flying. | 1.enter the url in the browser 2.https://examples.testsigma.com. 3.select the flight . | 1.Click on book now Button. | NA | The user should navigate to review page. |  | Pass
|  | TC ET 11 | Check User is able to book a flight after selecting going and return date in round trip flying option. | 1.enter the url in the browser 2.https://examples.testsigma.com. 3.select the flight . | 1.Click on book now Button. | NA | The user should navigate to review page. |  | pass
|  | TC ET 12 | Check User is able to book a flight after selecting going and return date in multi city flying option. | 1.enter the url in the browser 2.https://examples.testsigma.com. 3.select the flight . | 1.Click on book now Button. | NA | The user should navigate to review page. |  | Pass
|  | TC ET 13 | Check User is able to book a flight after selecting non stop and 1 stop option for stops. | 1.enter the url in the browser 2.https://examples.testsigma.com. 3.select the flight . | 1.Click on book now Button. | NA | The user should navigate to review page. |  | Pass
|  | TC ET 14 | Check User is able to book a flight after selecting arrival time. | 1.enter the url in the browser 2.https://examples.testsigma.com. 3.select the flight . | 1.Click on book now Button. | NA | The user should navigate to review page. |  | Pass
|  | TC ET 15 | Check User is able to book a flight after selecting departure time. | 1.enter the url in the browser 2.https://examples.testsigma.com. 3.select the flight . | 1.Click on book now Button. | NA | The user should navigate to review page. |  | Pass
|  | TC ET 16 | Check User is able to book a flight after selecting types of airlines | 1.enter the url in the browser 2.https://examples.testsigma.com. 3.select the flight . | 1.Click on book now Button. | NA | The user should navigate to review page. |  | Pass
|  | TC ET 17 | Check User is able to book a flight after sorting price | 1.enter the url in the browser 2.https://examples.testsigma.com. 3.select the flight . | 1.Click on book now Button. | NA | The user should navigate to review page. |  | Pass
|  | TC ET 18 | Check User is able to book a flight after sorting duration | 1.enter the url in the browser 2.https://examples.testsigma.com. 3.select the flight . | 1.Click on book now Button. | NA | The user should navigate to review page. |  | Pass
|  | TC ET 19 | Check User is able to book a flight after selecting travel class | 1.enter the url in the browser 2.https://examples.testsigma.com. 3.select the flight . | 1.Click on book now Button. | NA | The user should navigate to review page. |  | Pass
2 | Check the itinerary text is visible or not | TC ET 20 | Display the itinerary text | 1.enter the url in the browser 2.https://examples.testsigma.com. 3.select the flight . 4.click book now button. 5.navigate to review page | verify the display text | NA | The Text Should be visible |  | Pass
3 | Check the flight details is visible or not | TC ET 21 | Display the flight details | 1.enter the url in the browser 2.https://examples.testsigma.c om. 3.select the flight . 4.click book now button. 5.navigate to review page | verify the display of flight details in review book page | NA | Flight Details Should be there |  | Pass
4 | Check the arrival and departure details is available or not | TC ET 22 | Check arrival and departure details | 1.enter the url in the browser 2.https://examples.testsigma.c om. 3.select the flight . 4.click book now button. 5.navigate to review page | verify the details of arrival and verify the details of departure | NA | The arrival and departure details should be there |  | Pass
5 | Check that baggage details is visible or not below flight details | TC ET 23 | Check the baggage details | 1.enter the url in the browser 2.https://examples.testsigma.c om. 3.select the flight . 4.click book now button. 5.navigate to review page | verify display of text under Baggage Information | NA | Baggage Details Should be there |  | Pass
6 | Check that fare summary tab with all details is displaying correctly or not | TC ET 24 | Check that all fare summary details | 1.Enter the url in the browser https://examples.test sigma.com 2.select the flight and provide necessary information 3.Navigate the traveller page 4.Click on continue button 5.navigate to review page1.enter the url in the browser 2.https://examples.testsigma.c om. 3.select the flight . 4.click book now button. 5.navigate to review page | Check that all fare summary details | NA | The following details fare details,fees and surchanges,other services and total amount should be visiblw |  | Pass |  | Sai prathibha chenchireddy
7 | Check that cancellation and data change is visible or not | TC ET 25 | Check the cancellation and data change details | 1.enter the url in the browser 2.https://examples.testsigma.c om. 3.select the flight . 4.click book now button. 5.navigate to review page | Check the cancellation and data change details | NA | There should be cancellation and data change details0 - 2 hours* ADULT : Non Refundable ADULT : Non Changeable 2 - 24 hours* ADULT : attach_moneyUSD 3,000 + attach_moneyUSD 300 ADULT : attach_moneyUSD 2,500 + attach_moneyUSD 300 + Fare difference 1 - 365 days* ADULT : attach_moneyUSD 3,000 + attach_moneyUSD 300 ADULT : attach_moneyUSD 2,500 + attach_moneyUSD 300 + Fare difference |  | Pass
8 | Check that coupon code entering is correct or not | TC ET 26 | Check the coupon | 1.enter the url in the browser 2.https://examples.testsigma.c om. 3.select the flight . 4.click book now button. 5.navigate to review page | Check the coupon | NA | The User Should Enter Coupon Code |  | pass
9 | Check that baggage under important information is visible or not | TC ET 27 | Display the baggage information | 1.enter the url in the browser 2.https://examples.testsigma.c om. 3.select the flight . 4.click book now button. 5.navigate to review page | Display the all baggage information | NA | The user should be able to see the baggage information |  | pass
10 | Checks that Adds on text is visible or not below the important information | TC ET 28 | Display the Adds on text | 1.enter the url in the browser 2.https://examples.testsigma.c om. 3.select the flight . 4.click book now button. 5.navigate to review page | Displays the Adds on text | NA | The user should be able to view Adds on text |  | pass
11 | Check that all benefits are under the Adds on tab | TC ET29 | Verify the all benefits | 1.enter the url in the browser 2.https://examples.testsigma.c om. 3.select the flight . 4.click book now button. 5.navigate to review page | check the all benefit cancellation for medical reasons,loss of check in baggage,flight delay more than 11 hours,medical transport due to an accident,Transportation due to medical issue and some other | NA | The user should be able to see the all benefits |  | pass
12 | Check that select yes for conform the trip button is selected or not | TC ET 30 | Check the conform trip button | 1.enter the url in the browser 2.https://examples.testsigma.c om. 3.select the flight . 4.click book now button. 5.navigate to review page | click the conformation trip | NA | The user should be able to see the select yes buttonn |  | pass
13 | Check that button thanks for donating is checked or not | TC ET 31 | Check the thanks for donating button | 1.enter the url in the browser 2.https://examples.testsigma.c om. 3.select the flight . 4.click book now button. 5.navigate to review page | click the donating button | NA | The user should be able to see the selected button |  | pass
14 | Check that continue button is working or not | TC ET 32 | Check the continue button Functionality | 1.enter the url in the browser 2.https://examples.testsigma.c om. 3.select the flight . 4.click book now button. 5.navigate to review page | Click the continue button | NA | The User will navigate to Traveller Page |  | pass
15 | Check that flight summary text is visible or not | TC ET 33 | Display the flight text | 1.enter the url in the browser 2.https://examples.testsigma.c om. 3.select the flight . 4.click book now button. 5.navigate to review page 6.Click on continue page 7.Navigate to traveller page | Check the flight summary text | NA | Flight Summary will displayed |  | pass
16 | check that flight details link is working or not | TC ET 34 | Check the flight details link | 1.enter the url in the browser 2.https://examples.testsigma.c om. 3.select the flight . 4.click book now button. 5.navigate to review page 6.Click on continue page 7.Navigate to traveller page | Verify the flight details link by clicking the link | NA | Flight Dtails link in navigating to flight detail page |  | pass
17 | Check the traveller details text is visible or not | TC ET 35 | Display the traveller details text | 1.enter the url in the browser 2.https://examples.testsigma.c om. 3.select the flight . 4.click book now button. 5.navigate to review page 6.Click on continue page 7.Navigate to traveller page | Display the traveller details text belw the flight details link | NA | Traveller detail are displayed |  | pass
18 | check that add adults functionalities is working or not | TC ET 36 | Check the Add adults functionality | 1.enter the url in the browser 2.https://examples.testsigma.c om. 3.select the flight . 4.click book now button. 5.navigate to review page 6.Click on continue page 7.Navigate to traveller page | verify the Add adults functionalities | NA | Addults details are Added to the Travellers List |  | pass
19 | Check the first name and last name field is working or not | TC ET 37 | Check the first name and last name | 1.enter the url in the browser 2.https://examples.testsigma.c om. 3.select the flight . 4.click book now button. 5.navigate to review page 6.Click on continue page 7.Navigate to traveller page | verify the first name and verify the last name | First Name:Pratibha Last Name:Chenchiredy | User can enter his/her first name ,last name |  | Pass
20 | Check the radio button is working or not | TC ET 38 | check the radio button | 1.enter the url in the browser 2.https://examples.testsigma.c om. 3.select the flight . 4.click book now button. 5.navigate to review page 6.Click on continue page 7.Navigate to traveller page | select the male or female click the radio button | Male Or Female | Radio Button is working |  | Pass
21 | Verify the contact information like email and mobile number | TC ET 39 | verify the contact information | 1.enter the url in the browser 2.https://examples.testsigma.c om. 3.select the flight . 4.click book now button. 5.navigate to review page 6.Click on continue page 7.Navigate to traveller page | Verify the contact information mobile number and email id | verify the contact details like mobile no:9898787898 Email Id: pratibha@gmail.com | The user should able to see the contact information |  | Pass
22 | Verify the check box is working or not | TC ET 40 | check the check box for GsT business travel claim | 1.enter the url in the browser 2.https://examples.testsigma.c om. 3.select the flight . 4.click book now button. 5.navigate to review page 6.Click on continue page 7.Navigate to traveller page | 1.check the check box to claim credit 2.Write the Gst number | NA | The user should able to see the check box is checked |  | Pass
23 | Verify the acknowledgement checkbox is working or not | TC ET 41 | Check the Acknowledgment check box | 1.Enter the url in the browser https://examples.test sigma.com 2.select the flight and provide necessary information 3.Navigate the traveller page 4.Click on continue button 5.navigate to review page | Click the acknowledgement check box | NA | The user should be able to see acknowledgement check box is working |  | Pass
24 | Check whether the continue button is working or not | TC ET 42 | Check the continue button functionality | 1.enter the url in the browser 2.https://examples.testsigma.c om. 3.select the flight . 4.click book now button. 5.navigate to review page 6.Click on continue page 7.Navigate to traveller page | click the continue button | NA | User should be navigated to ancillary Page |  | Pass

## Travel and add ons
|  |  | Module Name | Travl and add ons
|  |  | Done By | Punita Jhamnani
REVIEW BOOKING
User Story | Functioanlity | Test case Id | Test Case Name | Pre Requisities | Test Case Steps | Test data | Expected Result | Status | Actual Results | Additional Comments | Testers
1 | Check User is able to navigate to ancillary page. | TC_AT_1 | Navigate to ancillary page | 1.Enter url in the browser https://examples.testsigma.com/ 2.select the flight and provide necessary information. 3.Navigate to the Traveller page. 4.fill required details & accept terms & condition by clicking checkbox. 5.click on continue button | Click the continue button | N/A | The user should navigate to the ancillary page | PASS
2 | Check User is able to see the text "Review Your Booking" or not . | TC_AT_2 | Display the text on the top of the ancillary page | 1.Enter url in the browser https://examples.testsigma.com/ 2.select the flight and provide necessary information. 3.Navigate to the Traveller page. 4.fill required details & accept terms & condition by clicking checkbox. 5.click on continue button. 6.Navigate to ancillary page. | Verify the display of text after the header section | N/A | The Text should be visible in white color with black background. | PASS
3 | Check user is able to see Status Bar or not . | TC_AT_3 | Display of Status Bar | 1.Enter url in the browser https://examples.testsigma.com/ 2.select the flight and provide necessary information. 3.Navigate to the Traveller page. 4.fill required details & accept terms & condition by clicking checkbox. 5.click on continue button. 6.Navigate to ancillary page. | Verify the display of status bar on the right side of the page after the text "Review Your Booking". | N/A | The status bar should display and highlighting the name of the page in white color. | PASS
4 | Check the Display of Meal Tab With its Object. | TC_AT_4 | Display of objects in Meal Tab | 1.Enter url in the browser https://examples.testsigma.com/ 2.select the flight and provide necessary information. 3.Navigate to the Traveller page. 4.fill required details & accept terms & condition by clicking checkbox. 5.click on continue button. 6.Navigate to ancillary page. | 1.Verify the display of Abbrevation name of Arrival and Departure City Name. 2.Verify the display of offer text in Meal Tab. 3.Verify the display of Select Condition in Meal Tab. | N/A | The Meal Tab should display the following objects:- 1.The display of abbrevation would be in white color with blue background in button format. 2.The offer text would be written in white color, blue background with icon. 3.The Select condition will be display below offer text. | PASS
5 | Check User is able to select "Non-Vegetarian Food Items"under Meal Tab with it's icon and amount. | TC_AT_5 | Display of Non-vegetarian food items | 1.Enter url in the browser https://examples.testsigma.com/ 2.select the flight and provide necessary information. 3.Navigate to the Traveller page. 4.fill required details & accept terms & condition by clicking checkbox. 5.click on continue button. 6.Navigate to ancillary page. | Verify the dispaly of Non-Vegetarian food items. | N/A | The Non-Vegetarian food Should display with its icon , amount and ADD Button functionality. | PASS
6 | Check User is able to select "Vegetarian Food Items "under Meal Tab with it's icon and amount. | TC_AT_6 | Display of Vegetarian food items | 1.Enter url in the browser https://examples.testsigma.com/ 2.select the flight and provide necessary information. 3.Navigate to the Traveller page. 4.fill required details & accept terms & condition by clicking checkbox. 5.click on continue button. 6.Navigate to ancillary page. | Verify the dispaly of Vegetarian food items. | N/A | The Vegetarian food Should display with its icon , amount and ADD Button functionality. | PASS
7 | Check User is able to add your preferred meal after clicking on the button "ADD". | TC_AT_7 | Check user is able to enter 1 meal item | 1.Enter url in the browser https://examples.testsigma.com/ 2.select the flight and provide necessary information. 3.Navigate to the Traveller page. 4.fill required details & accept terms & condition by clicking checkbox. 5.click on continue button. 6.Navigate to ancillary page. | Click on the ADD button to select your meal | N/A | The Food will be added. | PASS
|  | TC_AT_8 | Check user is able to enter more than 1 meal item | 1.Enter url in the browser https://examples.testsigma.com/ 2.select the flight and provide necessary information. 3.Navigate to the Traveller page. 4.fill required details & accept terms & condition by clicking checkbox. 5.click on continue button. 6.Navigate to ancillary page. | Click on the add button to select your meal | NA | The Food will be added. | FAIL | More than 1 food is not able to add.
8 | Check the Display of Footer Section With its Object in meal section. | TC_AT_9 | Display of The Footer section Object | 1.Enter url in the browser https://examples.testsigma.com/ 2.select the flight and provide necessary information. 3.Navigate to the Traveller page. 4.fill required details & accept terms & condition by clicking checkbox. 5.click on continue button. 6.Navigatae to ancillary page. | 1.Verify the display of number of food added by the User. 2.Verify the dispaly of total fare amount on the basis of food selected by user\ | N/A | User will get the display of number of selected food with its total fare amount . User can only select one item | PASS
9 | Check Reset Link is woking properly or not. | TC_AT_10 | Display the Reset link | 1.Enter url in the browser https://examples.testsigma.com/ 2.select the flight and provide necessary information. 3.Navigate to the Traveller page. 4.fill required details & accept terms & condition by clicking checkbox. 5.click on continue button. 6.Navigatae to ancillary page. | Click on the Reset link in the Footer tab | N/A | It should clear the Selected food item to 0. | PASS
10 | Check the Display of Baggage Tab With its Object. | TC_AT_11 | Display of objects in Baggage Tab | 1.Enter url in the browser https://examples.testsigma.com/ 2.select the flight and provide necessary information. 3.Navigate to the Traveller page. 4.fill required details & accept terms & condition by clicking checkbox. 5.click on continue button. 6.Navigate to ancillary page. | 1.Verify the display of Abbrevation name of Arrival and Departure City Name. 2.Verify the display of offer text in Baggage Tab. 3.Verify the display of Select Condition in Baggage Tab. | N/A | The Baggage tab will display the following objects:- 1.The display of abbrevation would be in white color with blue background in button format. 2.The offer text would be written in white color, blue background with icon. 3.The Select condition will be display below offer text. | PASS
11 | Check user is able to select "Additional 5 Kg"option under Baggage Tab with its icon and amount. | TC_AT_12 | Display of Additional 5 Kg option. | 1.Enter url in the browser https://examples.testsigma.com/ 2.select the flight and provide necessary information. 3.Navigate to the Traveller page. 4.fill required details & accept terms & condition by clicking checkbox. 5.click on continue button. 6.Navigate to ancillary page. | Verify the dispaly of Additional 5 Kg option. | N/A | The Additional 5g option Should display with its icon , amount and ADD Button functionality. | PASS
12 | Check user is able to select "Additional 10 Kg"option under Baggage Tab with its icon and amount. | TC_AT_13 | Display of Additional 10 Kg option. | 1.Enter url in the browser https://examples.testsigma.com/ 2.select the flight and provide necessary information. 3.Navigate to the Traveller page. 4.fill required details & accept terms & condition by clicking checkbox. 5.click on continue button. 6.Navigate to ancillary page. | Verify the dispaly of Additional 10 Kg option. | N/A | The Additional 10 kg option Should display with its icon , amount and ADD Button functionality. | PASS
13 | Check are you able to add extra baggage option after clicking on the button "ADD". | TC_AT_14 | Check user is able to enter 1 baggage item | 1.Enter url in the browser https://examples.testsigma.com/ 2.select the flight and provide necessary information. 3.Navigate to the Traveller page. 4.fill required details & accept terms & condition by clicking checkbox. 5.click on continue button. 6.Navigate to ancillary page. | Click on the ADD button to select your Extra Baggage Option | N/A | The Baggage will get added | PASS
|  | TC_AT_15 | Check user is able to enter more than 1 baggage item | 1.Enter url in the browser https://examples.testsigma.com/ 2.select the flight and provide necessary information. 3.Navigate to the Traveller page. 4.fill required details & accept terms & condition by clicking checkbox. 5.click on continue button. 6.Navigate to ancillary page. | Click on the ADD button to select your Extra Baggage Option | N/A | The Baggage will get added | FAIL | More than 1 baggage option is not able to add.
14 | Check the Display of Footer Section With its Object in Baggage section. | TC_AT_16 | Display of The Footer section Object | 1.Enter url in the browser https://examples.testsigma.com/ 2.select the flight and provide necessary information. 3.Navigate to the Traveller page. 4.fill required details & accept terms & condition by clicking checkbox. 5.click on continue button. 6.Navigatae to ancillary page. | 1.Verify the display of number of food added by the User. 2.Verify the dispaly of total fare amount on the basis of extra baggage selected by user. | N/A | User will get the display of number of selected extra Baggage with its total fare amount . User can only select one item | PASS
15 | Check "Continue" Button is navigating you to the next Page or not. | TC_AT_17 | Continue Button functionality | 1.Enter url in the browser https://examples.testsigma.com/ 2.select the flight and provide necessary information. 3.Navigate to the Traveller page. 4.fill required details & accept terms & condition by clicking checkbox. 5.click on continue button. 6.Navigatae to ancillary page. | Click on the Continue button | N/A | User Should Navigate to the Payment Page. | PASS

## Payment Gateway
|  |  | Module Name | Payment Gateway
|  |  | Done By | Punita Jhamnani
PAYMENT GATEWAY
User Story | Functioanlity | Test case Id | Test Case Name | Pre Requisities | Test Case Steps | Test data | Expected Result | Status | Actual Results | Additional Comments | Testers
1 | Check User is able to navigated on Payment Page. | TC_PT_1 | Navigate to payment page | 1.Enter url in the browser https://examples.testsigma.com/ 2.select the flight and provide necessary information. 3.Navigate to the Traveller page. 4.fill required details & accept terms & condition by clicking checkbox. 5.click on continue button 6.Navigate to ancillary page. | Click the continue button | N/A | The user should navigate to the payment page | PASS
2 | Check the "Simply Travel Wallet" text displayed on the top of the page or not. | TC_PT_2 | Display the text on the top of the payment | 1.Enter url in the browser https://examples.testsigma.com/ 2.select the flight and provide necessary information. 3.Navigate to the Traveller page. 4.fill required details & accept terms & condition by clicking checkbox. 5.click on continue button. 6.Navigate to ancillary page. 7.Click on Continue button. 8.Navigate to Payment Page | Verify the display of text after the header section | N/A | The user should able to see "Simply Travel Wallet" Text in grey color. | PASS
3 | Check the Details under "Simple Travel Wallet" text is displaying or not. | TC_PT_3 | Display the Objects under "Simple Travel wallet". | 1.Enter url in the browser https://examples.testsigma.com/ 2.select the flight and provide necessary information. 3.Navigate to the Traveller page. 4.fill required details & accept terms & condition by clicking checkbox. 5.click on continue button. 6.Navigate to ancillary page. 7.Click on Continue button. 8.Navigate to Payment Page | 1.Verify the display of TestSigma Wallet Balance. 2.Verify the display of Usable Balance. 3.Verify the display of Reward Bonus. 4.Verify the display of My Cash. 5.Verify the Link Add Amount. | N/A | The Following Objects should display under the "Simple Travel Wallet" text:- 1. TestSigma Wallet Total Balance. 2.Usable Balance. 3.Reward Bonus. 4.My Cash | PASS
4 | Check each and every Payment Option is working Properly or not under Payment Tab. | TC_PT_4 | Display The Payment Tab objects. | 1.Enter url in the browser https://examples.testsigma.com/ 2.select the flight and provide necessary information. 3.Navigate to the Traveller page. 4.fill required details & accept terms & condition by clicking checkbox. 5.click on continue button. 6.Navigate to ancillary page. 7.Click on Continue button. 8.Navigate to Payment Page | 1.Verify the display of top heading text . | N/A | Should display the text written on the top of the Paymnet Tab. | PASS
| Check each and every Payment Option is working Properly or not under Payment Tab. | TC_PT_5 | Display The Payment Tab objects. | 1.Enter url in the browser https://examples.testsigma.com/ 2.select the flight and provide necessary information. 3.Navigate to the Traveller page. 4.fill required details & accept terms & condition by clicking checkbox. 5.click on continue button. 6.Navigate to ancillary page. 7.Click on Continue button. 8.Navigate to Payment Page | 2.Verify the display of Mode of payment on the left side of payment tab. | N/A | Should Display the following Mode of Payment:- 1.UPI. 2. Net Banking. 3.Mobile wallet. 4.No Cost EMI 5.Paypal | PASS
5 | Check if you are able to select option under "UPI" mode of Payment. | TC_PT_6 | Check UPI Mode of Payment | 1.Enter url in the browser https://examples.testsigma.com/ 2.select the flight and provide necessary information. 3.Navigate to the Traveller page. 4.fill required details & accept terms & condition by clicking checkbox. 5.click on continue button. 6.Navigate to ancillary page. 7.Click on Continue button. 8.Navigate to Payment Page | 1.Click on the UPI mode of payment . 2.Select the best option. | N/A | The Following options will display under the UPI Mode of Payment:- 1.Keep registered VPA & Bank app on your phone. 2.Enter VPA on MakeMyTrip payment page. 3.MakeMyTrip will send a payment request. 4.Go to your banks app to access our request. 5.Go to transactions & enter MPIN to authenticate. 6.Your tickets will be booked after authentication. | FAIL | User is not able to select UPI Option,
6 | Check if you are able to select Major bank under "Net Banking" mode of Payment | TC_PT_7 | Check Net Banking Mode of Payment | 1.Enter url in the browser https://examples.testsigma.com/ 2.select the flight and provide necessary information. 3.Navigate to the Traveller page. 4.fill required details & accept terms & condition by clicking checkbox. 5.click on continue button. 6.Navigate to ancillary page. 7.Click on Continue button. 8.Navigate to Payment Page | 1.Click on the Net Banking mode of payment . 2.Select your bank name. | State Bank Of India | The Following options will display under the Net Banking Mode of Payment:- 1.Axis BAnk 2.CitiBank Bank Account online. 3.HDFC Bank. 4.ICICI Bank. 5.State Bank of India. | PASS
7 | Check if you are able to select option under "Mobile Wallet "mode of Payment. | TC_PT_8 | Check Mobile Wallet Mode of Payment | 1.Enter url in the browser https://examples.testsigma.com/ 2.select the flight and provide necessary information. 3.Navigate to the Traveller page. 4.fill required details & accept terms & condition by clicking checkbox. 5.click on continue button. 6.Navigate to ancillary page. 7.Click on Continue button. 8.Navigate to Payment Page | 1.Click on the Mobile Wallet mode of payment . 2.Select your bank name. | IDFC BANK | The Following options will display under the Mobile Wallet Mode of Payment:- 1.HDFC Bank. 2.IDFC Bank. 3.State Bank of India. | PASS
8 | Check if you are able to select option under No Cost EMI "mode of Payment. | TC_PT_9 | Check No Cost EMI Mode of Payment | 1.Enter url in the browser https://examples.testsigma.com/ 2.select the flight and provide necessary information. 3.Navigate to the Traveller page. 4.fill required details & accept terms & condition by clicking checkbox. 5.click on continue button. 6.Navigate to ancillary page. 7.Click on Continue button. 8.Navigate to Payment Page | 1.Click on the No Cost EMI mode of payment . 2.Select your bank name. | N/A | The Following options will display under the No Cost EMI Mode of Payment:- 1.Airtel Money 2.Amazon Pay 3.Itz Cash Card. 4.Mobiwik -Up to 5.PayZapp. | PASS
9 | Check if you are able to select type of money under "Paypal" mode of Payment. | TC_PT_10 | Check Paypal Mode of Payment | 1.Enter url in the browser https://examples.testsigma.com/ 2.select the flight and provide necessary information. 3.Navigate to the Traveller page. 4.fill required details & accept terms & condition by clicking checkbox. 5.click on continue button. 6.Navigate to ancillary page. 7.Click on Continue button. 8.Navigate to Payment Page | 1.Click on thePaypal mode of payment . 2.Select type of Money. | N/A | The Following options will display under the No Cost EMI Mode of Payment:- 1.EUR(EURO) 2.GBP(British Pound) 3.HKD(Hong Kong Dollar ) 4.SGD(Singapore Dollar) 5.THB(Thai Baht) 6.USD(United State Dollar) | PASS
10 | Check the "Finish Payment" Button functionality. | TC_PT_11 | Check "Finish Payment" Button functionality | 1.Enter url in the browser https://examples.testsigma.com/ 2.select the flight and provide necessary information. 3.Navigate to the Traveller page. 4.fill required details & accept terms & condition by clicking checkbox. 5.click on continue button. 6.Navigate to ancillary page. 7.Click on Continue button. 8.Navigate to Payment Page | Click on the Finish Payment Button | N/A | 1.Flight should be booked. 2.The user should be navigate to booking summary page. | PASS

## Booking Summary
|  |  | Module Name | Booking Summary
|  |  | Done By | Punita Jhamnani
BOOKING SUMMARY
User Story | Functioanlity | Test case Id | Test Case Name | Pre Requisities | Test Case Steps | Test data | Expected Result | Status | Actual Results | Additional Comments | Testers
1 | Check the Final details under Successfully Booked Ticket Tab that is comprises of Flight name,Duration of journey,Time of Flight amd Total price. | TC_BT_1 | Check Succesfully Booked Ticket Tab | 1.Enter url in the browser https://examples.testsigma.com/ 2.select the flight and provide necessary information. 3.Navigate to the Traveller page. 4.fill required details & accept terms & condition by clicking checkbox. 5.click on continue button. 6.Navigate to ancillary page. 7.Click on Continue button. 8.Navigate to Payment Page 9.Click on Finish Payment Button . | 1.Verify the Display of Flight name. 2.Verify the details of Arrival and depature date and time. 3.Verify the Total Amount. | N/A | The Following options will display under the Successfully Booked Ticket:- 1.Flight Name. 2.Arrival Date And Time. 3.Departure Date And Time. 4.Total Amount. | PASS
2 | Check the Book Summary Tab on the right hand side of the page. | TC_BT_2 | Check Booking Summary | 1.Enter url in the browser https://examples.testsigma.com/ 2.select the flight and provide necessary information. 3.Navigate to the Traveller page. 4.fill required details & accept terms & condition by clicking checkbox. 5.click on continue button. 6.Navigate to ancillary page. 7.Click on Continue button. 8.Navigate to Payment Page 9.Click on Finish Payment Button . | 1.Verify the Display of Flight name. 2.Verify the details of Arrival and depature date,time and Place. 3.Verify the display of Duration Time. 4.Verify thedisplay of number of Travelers. 5.Verify the display of contact details. 6.Verify the Display of Amount. | N/A | The Booking Summary Tab will display the following Display in the right side of the Successfully Booked Ticket Text :- 1.Flight Name. 2.Arrival Date , Time and Place. 3.Departure Date,Time and Place. 4.Duration of flight. 6.No of Adult. 7.No of Infants. 8.No. of Childs 9.Insurance Included or not. 10.Charity Donation included or not. 11.Contact Details. 12.Sub Total. 13.Donate to cause. 14.Convenience Fee 15.Total Amount | PASS

## Logout
|  |  |  | Module Name | Logout
|  |  |  | Done by | Radha Panchal
LOGOUT PAGE
User story | Functionalities | Test Case Id | Test Case Name | Pre-Requisities | Test case steps | Test Data | Expected Result | Status | Actual Result | Additional comment | Tester
1 | verify After successfull login click on profile icon to check logout button is visible or not | TC_Log_001 | check user is able to selecting logout Option from' My Account' dropmenu. | 1.Open the Application Url 2.User is logged in | 1. click on 'My Account' dropmenu 2.Select Logout option | N/A | 1.User should be taken to 'Logout Account'page and user should see login option in place of logout under 'My Account dropmenu' 2.user should taken to the home page. | Pass
2 | Verify logout option from by selecting 'Right coloumn' option. | TC_Log_00 2 | Check user is able to logout option from by selecting' Right coloumn' option. | 1.open the Application Url 2.User is Logged in and is on 'Account Page' | 1. click on' Logout 'Option from the Right column 2.click on'continue' button | N/A | 1.User should be taken to 'Logout Account'page and user should see login option in place of logout under 'My Account dropmenu' 2.user should taken to the home page. | Pass
3 | Verify, the Application Login session status,after logging and closing the browser without logging out. | TC_Log_003 | check the Application Login session status | 1.open the Application Url 2.User is Logged in | 1.close the browser without Logging out 2.Open the browser and navigate the application | N/A | 1.Application should not get logged out instead the user logged in session need to be mentained. | Pass
4 | Verify logout option is not displayed under 'My Account'. | Tc_Log_005 | check logout button is displayed or not | 1.Open the Application url | 1.check on 'My Account Dropmenu'. | N/A | 1.Logout Option should not be displayed under 'My Account 'dropmenu. | Pass
5 | verify logout option is not displayed under 'Right Column'option before you login. | Tc_Log_006 | check user is able display logout option or not | 1.Open the Application url | 1.check on 'My Account Dropmenu 2.select 'Register' option | N/A | 1.Logout option should not be displayed in the 'Right Column'. | Pass
6 | Verify Logout option is clickable or not | Tc_Log_007 | Check logout button is able clickable or not | 1.open the Application Url 2.User is Logged in | 1.check on'My Account Dropmenu'. | N/A | 1. user able to click Logout button successfully. | Pass

## Defect Report
Defect ID | MODULE NAME | DEFECT SUMMARY | Steps to reproduce | PRIORITY | Severity | ASSIGNEE | REPORTER | STATUS
DF_01 | Registration | Blank spaces in required fields are accepting and should show validation error message | 1. Launch the Browser. 2. Click on the Signup button on homepage. 3. Pass blank spaces in all required fields. 4. Click on the Register button | High | Critical | Radha Panchal | Reshma K.R | To Do
DF_02 | Registration | The Fullname field accepts number and special character | 1. Launch the Browser. 2. Click on the Signup button on homepage. 3. Enter number and special character in the Fullname field 4. Click on the Register button | High | Critical | Radha Panchal |  | To Do
DF_03 | Registration | The email validation of not valid cases are not implemented like .com | 1. Launch the Browser. 2. Click on the Signup button on homepage. 3. Enter valid details in all required fields. 4.Enter email id without .com 5. Click on the Register button | High | Critical | Radha Panchal |  | To Do
DF_04 | Registration | User should not be able to register with already registered email id | 1. Launch the Browser. 2. Click on the Signup button on homepage. 3. Enter valid details in all required fields. 4.Enter already existed email id 5. Click on the Register button | Medium | Moderate | Radha Panchal |  | To Do
DF_05 | Registration | System should not accept special character and alphabets in phone number fields | 1. Launch the Browser. 2. Click on the Signup button on homepage. 3. Enter valid details in all required fields. 4.Enter special character and alphabet in phone number field 5. Click on the Register button | High | Critical | Punita Jhamnani |  | To Do
DF_06 | Registration | User should not be able to register with already registered phone number | 1. Launch the Browser. 2. Click on the Signup button on homepage. 3. Enter valid details in all required fields. 4.Enter already existed phone number 5. Click on the Register button | Medium | Moderate | Punita Jhamnani |  | To Do
DF_07 | Registration | System is accepting the password length more than 16 characters and less than 6 character, so we have to set password length for user and can enter password between 6 to 16 characters. | 1. Launch the Browser. 2. Click on the Signup button on homepage. 3. Enter valid details in all required fields. 4. Enter password more than 16 characters and less than 6 character 5. Click on the Register button | High | Critical | Punita Jhamnani |  | To Do
DF_09 | Registration | Selected image should be in restricted size and must show error message if size limit exceeded | 1. Launch the Browser. 2. Click on the Signup button on homepage. 3. Enter valid details in all required fields. 4. click on upload picture button 5. Select image to upload 6. Click on the Register button | Low | Minor | Punita Jhamnani |  | To Do
DF_10 | Registration | Images uploaded while registering are not uploaded in profile section | 1. Launch the Browser. 2. Click on the Signup button on homepage. 3. Enter valid details in all required fields. 4. click on upload picture button 5. Select image to upload 6. Click on the Register button 7. View profile section | Low | Minor | Punita Jhamnani |  | To Do
DF_11 | LOGIN | User is not able to Login with valid username and valid Password. | 1. Launch the Browser. 2. click on the Login button on homepage. 3.Enter valid datails. 4. click on Login Button. | High | Critical | Sai prathibha chenchireddy | Radha Panchal | To Do
DF_12 | LOGIN | System should generate validation error message when passsword field entered is blank | 1. Launch the Browser. 2. click on the Login button on homepage. 3.Enter valid datails as valid username and Password 4.click on Login Button | High | Critical | Sai prathibha chenchireddy |  | To Do
DF_13 | LOGIN | User is not able to set new password | 1. Launch the Browser. 2. click on the Login button on homepage. 3.Enter valid datails as valid username and Password 4. click on forgot password. | Medium | Moderate | Sai prathibha chenchireddy |  | To Do
DF_14 | LOGIN | User is not getting reset password link | 1. Launch the Browser. 2. click on the Login button on homepage. 3.if you Enter details as invalid username and Password 4. click on forgot password. 5.Enter mail for Reset password link . 6.Check link on mail for reset password. | Medium | Moderate | Sai prathibha chenchireddy |  | To Do
DF_15 | Search a Flight | user is not able to click on search button for one way flying, two way flying and also round trip flying | 1. Launch the Browser. 2. Navigate to homepage page. 3. Click on the Go To Travel Button. 4.Click on the one way flying, two way flying and also round trip button. 5.Click on that search button. | High | Critical | Ruchita Sapkal | Ruchita Sapkal | To Do
DF_16 | Search a Flight | user is not able to apply filter for one way flying, two way flying and also round trip flying | 1. Launch the Browser. 2. Navigate to homepage page. 3. Click on the Go To Travel Button. 4.Click on the one way flying, two way flying and also round trip button. 5.Enter search value in search box that is available in database. 6. Go to the Search Filter 7. Select/click on the checkbox. | High | Critical | Ruchita Sapkal |  | To Do
DF_17 | Search a Flight | user is not able to reset filter for one way flying, two way flying and also round trip flying | 1. Launch the Browser. 2. Navigate to homepage page. 3. Click on the Go To Travel Button. 4.Click on the one way flying, two way flying and also round trip button. 5.Enter search value in search box that is available in database. 6. Go to the Search Filter 7. Select/click on the checkbox. 8.Click on the reset button. | High | Critical | Ruchita Sapkal |  | To Do
DF_18 | Search a Flight | user is not able to sort flight for one way flying, two way flying and also round trip flying | 1. Launch the Browser. 2. Navigate to homepage page. 3. Click on the Go To Travel Button. 4.Click on the one way flying, two way flying and also round trip button. 5.Enter search value in search box that is available in database. 6. Go to the Search sort. 7. Select/click on the checkbox. | High | Critical | Ruchita Sapkal |  | To Do
DF_19 | Review Booking | user is not able to book more than 12 persons | 1.click on paasengers and class 2.select more than 12 guests 3. see you will not able to do this. | High | Critical | Ruchita Sapkal | Sai prathibha chenchireddy | To Do
DF_20 | Travel and add ons | User is not able to enter more than 1 meal item | 1.Navigate to the Travel And addons page. 2.Click on Meal Tab. 3.Select More Than 2 Option and 4.See you are not able to do this | High | Critical | Ruchita Sapkal | Punita Jhamnani | To Do
DF_21 | Travel and add ons | User is not able to enter more than 1 baggage item | 1.Navigate to the Travel And addons page. 2.Click on Baggage Tab. 3.Select More Than 2 Option and 4.See you are not able to do this . | High | Critical | Ruchita Sapkal |  | To Do
DF_22 | Payment Gateway | User is not able to select option under "UPI" mode of payment | 1.Navigate to Payment Page . 2.Browse under Payment Tab. 3.Select UPI Option. 4.Select any option under UPI tab and 5. See you will not be able to do this | High | Critical | Ruchita Sapkal |  | To Do

## Traceability Matrix
REQUIREMENTS TRACEABILITY MATRIX
Project Name: |  | Example Travel
National Center: |  | Cap Gemeni
Project Manager Name: |  | Naresh
Project Description: |  | Flight Booking
ID | Assoc ID | Technical Assumption(s) and/or Customer Need(s) | Functional Requirement | Status | Architectural/Design Document | Technical Specification | System Component(s) | Software Module(s) | Test Case Number | Tested In | Implemented In | Verification | Additional Comments
REGISTRATION
1 | 1.1.1 | Signup button | Check display of Signup button | Completed | Completed |  |  | Not required | TC_Reg_01 | Windows |  | Done
2 | 2.2.2 | Register page | Navigate to Register page and display the header and text/line of registration page | Completed | Completed |  |  | Not required | TC_Reg_02 TC_Reg_03 TC_Reg_04 | Windows |  | Done
3 | 3.3.3 | Validate all the Required fields | Verify by fiiling and not filling any data | Completed | Completed |  |  | Not required | TC_Reg_05 TC_Reg_06 | Windows |  | Done
|  |  | Verify if blank spaces are passed | Testing | Completed |  |  | Not required | TC_Reg_07 | Windows |  | No | DF_001: Not showing error message when blank space are passed
4 | 4.4.4 | Fullname field | Verify numbers and special character are not allowed | Testing | Completed |  |  | Not required | TC_Reg_08 TC_Reg_09 | Windows |  | No | DF_002: Not showing error message when numbers and special character are entered
5 | 5.5.5 | Email field | Verify the system is accepting all the valid email address or not. | Completed | Completed |  |  | Not required | TC_Reg_10 | Windows |  | Done
|  |  | Verify for some invalid emails with cases and should not be able to registered with valid but duplicate/existing email address. | Testing | Completed |  |  | Not required | TC_Reg_11 TC_Reg_12 | Windows |  | No | DF_003: should display error message when .com is not entered and already existed email id is entered
6 | 6.6.6 | Phone number field | Verify the system is accepting all the valid phone number or not. | Completed | Completed |  |  | Not required | TC_Reg_13 | Windows |  | Done
|  |  | Validate for some invalid phone number with cases and should not be able to registered with valid but duplicate/ already existing phone number. | Testing | Completed |  |  | Not required | TC_Reg_14 TC_Reg_15 | Windows |  | No | DF_004: display error message when number and special character and already registered number are entered
7 | 7.7.7 | Age group radio button | Verify that user is able to select only single value for Age group option by clicking on radio button. | Completed | Completed |  |  | Not required | TC_Reg_16 | Windows |  | Done
8 | 8.8.8 | Gender group radio button | Verify that user is able to select only single value for Gender option by clicking on radio button. | Completed | Completed |  |  | Not required | TC_Reg_17 | Windows |  | Done
9 | 9.9.9 | Hobbies checkbox | Verify that user is able to select value for hobbies option by clicking on checkbox button. | Completed | Completed |  |  | Not required | TC_Reg_18 | Windows |  | Done
10 | 10.10.10 | Interests checkbox | Verify that user is able to select value for interests option by clicking on checkbox button. | Completed | Completed |  |  | Not required | TC_Reg_19 | Windows |  | Done
11 | 11.11.11 | Password validation with all combinations | Verify that password fields should be encrypted with * symbol and should contains a special characters, lowercase, uppercase and numbers. | Completed | Completed |  |  | Not required | TC_Reg_20 TC_Reg_23 | Windows |  | Done
|  |  | Validate the password value not be less than 6 characters and not more than 16 characters | Testing | Completed |  |  | Not required | TC_Reg_21 TC_Reg_22 | Windows |  | No | DF_005: it accepts less than 6 and more than 16 character
12 | 12.12.12 | Password and confirm password | Verify if the Password and Confirm Password fields are accepting similar values only. | Completed | Completed |  |  | Not required | TC_Reg_24 | Windows |  | Done
|  |  | Verify when enter mismatch values in both password and confirm password fields. | Testing | Completed |  |  | Not required | TC_Reg_25 | Windows |  | No | DF_006: display error message when entered mismatch values
13 | 13.13.13 | Profile picture | Validate profile picture buttion is workable, Navigate to location page to upload and images are uploaded in input fiels | Completed | Completed |  |  | Not required | TC_Reg_26 TC_Reg_27 TC_Reg_30 | Windows |  | Done
|  |  | Verify the restriction size and Images are uploaded in the profile section | Testing | Completed |  |  | Not required | TC_Reg_29 TC_Reg_31 | Windows |  | No | DF_007: images should be in restricted size limit and are not displayed in profile section
14 | 14.14.14 | Register button | Verify the user is able to register by clicking on register button | Completed | Completed |  |  | Not required | TC_Reg_32 | Windows |  | Done
|  |  | Navigate to appropriate page after successful register. |  | Completed |  |  | Not required | TC_Reg_33 | Windows |  | Done
LOGIN
1 | 1.1.1 | Navigate to Login page | Display of the Login page | Completed | Completed |  |  | Not required | TC_Log1 | Windows |  | Done
2 | 2.2.2 | verify if a user will be able to login with a valid username and valid password. | check User is able to login valid username and password or not | Testing | Completed |  |  | Not required | TC_Log2 | Windows |  | NO | DF_11:user is not able to login with valid username and valid password.
3 | 3.3.3 | Verify the Login functionality with invalid username and an valid password. | check User is unable to login with invalid email and valid password | Completed | Completed |  |  | Not required | TC_Log3 | Windows |  | Done
4 | 4.4.4 | Verify the Login functionality with valid username and an invalid password. | check user is able to Login with valid username and invalid password | Completed | Completed |  |  | Not required | TC_Log4 | Windows |  | Done
5 | 5.5.5 | Verify the user is login with blank username | check user is unable to login with blank username | Completed | Completed |  |  | Not required | TC_Log5 | Windows |  | Done
6 | 6.6.6 | verify the user is able to login with blank password | check User is unable to login with blank password. | Testing | Completed |  |  | Not required | TC_Log6 | Windows |  | No | DF_12:System should generate validation error message when passsword field entered is blank
7 | 7.7.7 | verify the user is able to fill "password"in the textbox. | check the user is taken to loginwithvalid password | Completed | Completed |  |  | Not required | TC_Log7 | Windows |  | Done
8 | 8.8.8 | Verify if the data in password field is either visible as asterisk or bullet signs | check if user is display password field is visible as asterisk or not | Completed | Completed |  |  | Not required | TC_Log8 | Windows |  | Done
9 | 9.9.9 | check the user is able to navigate forget password option | check user is able to navigate forgot password option | Completed | Completed |  |  | Not required | TC_Log9 | Windows |  | Done
10 | 10.10.10 | verify if a user is able to login with a new password only after he/she has changed the password. | check user Is able to login with new password or not | Testing | Completed |  |  | Not required | TC_Log10 | Windows |  | No | DF_13:User is not able to set new password.
11 | 11.11.11 | Verify if the ‘Login’ key of the keyboard is working correctly on the login page. | check user is able to login valid username and invalid password | Completed | Completed |  |  | Not required | TC_Log11 | Windows |  | Done
12 | 12.12.12 | Verify if user enter invalid data then user is able to see error message | check user is enter login valid username and invalid password error mesaage is displayed or not | Completed | Completed |  |  | Not required | TC_Log12 | Windows |  | Done
13 | 13.13.13 | Verify the user is able to enter valid data & get successfull login. | check user is able to enter valid data and get successfull Login or not. | Testing | Completed |  |  | Not required | TC_Log13 | Windows |  | NO | DF_14:User is not able to login successfully.
SEARCH FLIGHT
1 | 1.1.1 | Navigate to search flight page. | check the user is able to navigate through Go To Travel button. | Completed | Completed |  |  | Not required | TC ET 01 | Windows |  | Done
2 | 2.2.2 | Navigate to search flight page. | check the user to display one way flying , round trip flying, multicity button. | Completed | Completed |  |  | Not required | TC ET 02 | Windows |  | Done
3 | 3.3.3 | Navigate to search flight page. | check the user can navigate to one way flying page using button. | Completed | Completed |  |  | Not required | TC ET 03 | Windows |  | Done
4 | 4.4.4 | search result page for city you are going to fly from and fly to. | check are you able to city you are going to fly from and fly to. | Completed | Completed |  |  | Not required | TC ET 04 | Windows |  | Done
5 | 5.5.5 | navigating to departure button | check the departure button. | Completed | Completed |  |  | Not required | TC ET 05 | Windows |  | Done
6 | 6.6.6 | departure date | check you should enter the date of departing . | Completed | Completed |  |  | Not required | TC ET 06 | Windows |  | Done
7 | 7.7.7 | search flight for adults ,children and infant and it should not exceed 12 and then select class Economicy ,Premium economy, Business, First Class. | check number of passengers (adults ,children and infant) and it should not exceed 12 and then select class (Economicy ,Premium economy, Business, First Class) then press the done button. | Completed | Completed |  |  | Not required | TC ET 07 | Windows |  | Done
8 | 8.8.8 | search result page | check once you enter all the necessary information and press the Done button, you will be redirected to the page with search results. Here you can find recommended content that matches your criteria a diverse number of flights available. | Testing | Completed |  |  | Not required | TC ET 08 | Windows |  | no | DF_15: user is not able to click on search button for one way flying, two way flying and also round trip flying
9 | 9.9.9 | search sorted flight | Check from top you can apply the Sort and Filter functionality to find a flight based on your specific needs and requirements. | Testing | Completed |  |  | Not required | TC ET 09 | Windows |  | No | DF_16: user is not able to apply filter for one way flying, two way flying and also round trip flying
10 | 10.10.10 | search filter flight | Check the filters are applied in real time that means you don’t need to press the Confirm button to see them applied. Sort and Filter functionality allows you to sort filters that you want to be applied. a. number of stops; b. airlines; c. lowest and highest price; | Testing | Completed |  |  | Not required | TC ET10 | Windows |  | No | DF_17: user is not able to reset filter for one way flying, two way flying and also round trip flying
11 | 11.11.11 | all reset button | Check once you can press the Reset button to reset all the information selected in one click. | Testing | Completed |  |  | Not required | TC ET 11 | Windows |  | No | DF_18: user is not able to sort flight for one way flying, two way flying and also round trip flying
12 | 12.12.12 | Check the flight detail and if necessary Chabge the essential if necessary, | Check you have selected the flight, you can press the Apply button. Then you will be shown a range of airlines for returning flights to choose from and redirected to the trip summary page. | Completed | Completed |  |  | Not required | TC ET 12 | Windows |  | Done
13 | 13.13.13 | all flight information display | Verify you can see information about the flight, see flight and baggage fee details, change flights if it is necessary and then continue the Booking process. | Completed | Complete |  |  | Not required | TC ET 13 | Windows |  | Done
14 | 14.14.14 | search result page | check the user can navigate to Round Trip Flying page using button. | Completed | Completed |  |  | Not required | TC ET 14 | Windows |  | Done
15 | 15.15.15 | search result page | check the user can navigate to Round Trip Flying page using button. | Completed | Completed |  |  | Not required | TC ET 15 | Windows |  | Done
16 | 16.16.16 | search result page | check are you able to city you are going to fly from and fly to. | Completed | Completed |  |  | Not required | TC ET 16 | Windows |  | Done
17 | 17.17.17 | navigating to departure button | check the departure button. | Completed | Completed |  |  | Not required | TC ET 17 | Windows |  | Done
18 | 18.18.18 | departure date | check you should enter the date of departing . | Completed | Completed |  |  | Not required | TC ET 18 | Windows |  | Done
19 | 19.19.19 | search flight for adults ,children and infant and it should not exceed 12 and then select class Economicy ,Premium economy, Business, First Class. | check number of passengers (adults ,children and infant) and it should not exceed 12 and then select class (Economicy ,Premium economy, Business, First Class) then press the done button. | Completed | Completed |  |  | Not required | TC ET 19 | Windows |  | Done
20 | 20.20.20 | search result page | check once you enter all the necessary information and press the Done button, you will be redirected to the page with search results. Here you can find recommended content that matches your criteria a diverse number of flights available. | Testing | Completed |  |  | Not required | TC ET 20 | Windows |  | No | DF_15: user is not able to click on search button for one way flying, two way flying and also round trip flying
21 | 21.21.21 | search sorted flight | Check from top you can apply the Sort and Filter functionality to find a flight based on your specific needs and requirements. | Testing | Completed |  |  | Not required | TC ET 21 | Windows |  | No | DF_16: user is not able to apply filter for one way flying, two way flying and also round trip flying
22 | 22.22.22 | search filter flight | Check the filters are applied in real time that means you don’t need to press the Confirm button to see them applied. Sort and Filter functionality allows you to sort filters that you want to be applied. a. number of stops; b. airlines; c. lowest and highest price; | Testing | Completed |  |  | Not require | TC ET 22 | Windows |  | No | DF_17: user is not able to reset filter for one way flying, two way flying and also round trip flying
23 | 23.23.23 | all reset button | Check once you can press the Reset button to reset all the information selected in one click. | Testing | Completed |  |  | Not required | TC ET 23 | Windows |  | No | DF_18: user is not able to sort flight for one way flying, two way flying and also round trip flying
24 | 24.24.24 | all flight information display | Check you have selected the flight, you can press the Apply button. Then you will be shown a range of airlines for returning flights to choose from and redirected to the trip summary page. | Completed | Completed |  |  | Not required | TC ET 24 | Windows |  | Done
25 | 25.25.25 | all flight information display | Verify you can see information about the flight, see flight and baggage fee details, change flights if it is necessary and then continue the Booking process. | Completed | Completed |  |  | Not required | TC ET 25 | Windows |  | Done
26 | 26.26.26 | search result page | check the user can navigate to Multicity Flying page using button. | Completed | Completed |  |  | Not required | TC ET 26 | Windows |  | Done
27 | 27.27.27 | search result page | check the user can navigate to Multicity Flying page using button. | Completed | Completed |  |  | Not required | TC ET 27 | Windows |  | Done
28 | 28.28.28 | search result page | check are you able to city you are going to fly from and fly to. | Completed | Completed |  |  | Not required | TC ET 28 | Windows |  | Done
29 | 29.29.29 | navigating to departure button | check the departure button. | Completed | Completed |  |  | Not required | TC ET 29 | Windows |  | Done
30 | 30.30.30 | departure date | check you should enter the date of departing . | Completed | Completed |  |  | Not required | TC ET 30 | Windows |  | Done
31 | 31.31.31 | search flight for adults ,children and infant and it should not exceed 12 and then select class Economicy ,Premium economy, Business, First Class. | check number of passengers (adults ,children and infant) and it should not exceed 12 and then select class (Economicy ,Premium economy, Business, First Class) then press the done button. | Completed | Completed |  |  | Not required | TC ET 31 | Windows |  | Done
32 | 32.32.32 | search result page | check once you enter all the necessary information and press the Done button, you will be redirected to the page with search results. Here you can find recommended content that matches your criteria a diverse number of flights available. | Testing | Completed |  |  | Not required | TC ET 32 | Windows |  | No | DF_15: user is not able to click on search button for one way flying, two way flying and also round trip flying
33 | 33.33.33 | search sorted flight | Check from top you can apply the Sort and Filter functionality to find a flight based on your specific needs and requirements. | Testing | Completed |  |  | Not required | TC ET 33 | Windows |  | No | DF_16: user is not able to apply filter for one way flying, two way flying and also round trip flying
34 | 34.34.34 | search filter flight | Check the filters are applied in real time that means you don’t need to press the Confirm button to see them applied. Sort and Filter functionality allows you to sort filters that you want to be applied. a. number of stops; b. airlines; c. lowest and highest price; | Testing | Completed |  |  | Not required | TC ET 34 | Windows |  | No | DF_17: user is not able to reset filter for one way flying, two way flying and also round trip flying
35 | 35.35.35 | all reset button | Check once you can press the Reset button to reset all the information selected in one click. | Testing | Completed |  |  | Not required | TC ET 35 | Windows |  | No | DF_18: user is not able to sort flight for one way flying, two way flying and also round trip flying
36 | 36.36.36 | all flight information display | Check you have selected the flight, you can press the Apply button. Then you will be shown a range of airlines for returning flights to choose from and redirected to the trip summary page. | Completed | Completed |  |  | Not required | TC ET 36 | Windows |  | Done
37 | 37.37.37 | all flight information display | Verify you can see information about the flight, see flight and baggage fee details, change flights if it is necessary and then continue the Booking process. | Completed | Completed |  |  | Not required | TC ET 37 | Windows |  | Done
Review your Booking
1 | 1.1.1 | click book now button | check user able to book a flight afer clicking book now from predefined flights | completed | completed |  |  | Not required | TC ET 01 | Windows |  | Done
2 | 2.2.2 | click book now button | check user able to book a flight after searching for particular flight details | completed | completed |  |  | Not required | TC ET 02 | windows |  | Done
3 | 3.3.3 | click book now button | check user is able to book a flight after selectingb1 adult and 1 child | completed | completed |  |  | Not required | TC ET 03 | windows |  | Done
4 | 4.4.4 | click book now button | check user is able to book a flight after selecting 1 adult and more than 1 child | completed | completed |  |  | Not required | TC ET O4 | windows |  | Done
5 | 5.5.5 | click book now button | check user book flight after selecting more 12 persons | Testing | In progress |  |  | not required | TC ET O5 | windows |  | No | DF_019:user is not able to select more than 12 persons
6 | 6.6.6 | click book now button | check user is able to book a flight selecting 1 child and more than 1 adult | completed | completed |  |  | not required | TC ET 06 | windows |  | Done
7 | 7.7.7 | click book now button | check user is able to book a flight after selecting departure place | completed | completed |  |  | Not required | TC ET O7 | windows |  | Done
8 | 8.8.8 | click book now button | check user is able to book a flight after selecting place from where to fly | completed | completed |  |  | Not required | TC ET 08 | Windows |  | Done
9 | 9.9.9 | click book now button | check user is able to book a flight after selecting departure and current place | completed | completed |  |  | Not required | TC ET 09 | Windows |  | Done
10 | 10.10.10 | click book now button | check user is able to book a flight after booking a particular date in one way flying | completed | completed |  |  | Not required | TC ET 10 | Windows |  | Done
11 | 11.11.11 | click book now button | check user is able to book a flight after selecting going abd return date in round trip flying | completed | completed |  |  | Not required | TC ET 11 | Windows |  | Done
12 | 12.12.12 | click book now button | Check User is able to book a flight after selecting going and return date in multi city flying option. | completed | completed |  |  | Not required | TC ET 12 | Windows |  | Done
13 | 13.13.13 | click book now button | Check User is able to book a flight after selecting non stop and 1 stop option for stops. | completed | completed |  |  | Not required | TC ET 13 | Windows |  | Done
14 | 14.14.14 | click book now button | Check User is able to book a flight after selecting arrival time. | completed | completed |  |  | Not required | TC ET 14 | Windows |  | Done
15 | 15.15.15 | click book now button | Check User is able to book a flight after selecting departure time. | completed | completed |  |  | Not required | TC ET 15 | Windows |  | Done
16 | 16.16.16 | click book now button | Check User is able to book a flight after selecting types of airlines | completed | completed |  |  | Not required | TC ET 16 | Windows |  | Done
17 | 17.17.17 | click book now button | Check User is able to book a flight after sorting price | completed | completed |  |  | Not required | TC ET 17 | Windows |  | Done
18 | 18.18.18 | click book now button | Check User is able to book a flight after sorting duration | completed | completed |  |  | Not required | TC ET 18 | Windows |  | Done
19 | 19.19.19 | click book now button | Check User is able to book a flight after selecting travel class | completed | completed |  |  | Not required | TC ET 19 | Windows |  | Done
20 | 20.20.20 | check itinerary text | Display the itinerary text | completed | completed |  |  | NOt required | TC ET 20 | Windows |  | Done
21 | 21.21.21 | check flight details | Display the flight details | completed | completed |  |  | NOt required | TC ET 21 | Windows |  | Done
22 | 22.22.22 | check arrival and departure detail | Check arrival and departure details | completed | completed |  |  | NOt required | TC ET 22 | Windows |  | Done
23 | 23.23.23 | verify baggage details | Check the baggage details | completed | completed |  |  | NOt required | TC ET 23 | Windows |  | Done
24 | 24.24.24 | check fare summary details | Check that all fare summary details | completed | completed |  |  | NOt required | TC ET 24 | Windows |  | Done
25 | 25.25.25 | verify cancel and date change detail | Check the cancellation and data change details | completed | completed |  |  | NOt required | TC ET 25 | Windows |  | Done
26 | 26.26.26. | verify the coupon code | Check the coupon | completed | completed |  |  | NOt required | TC ET 26 | Windows |  | Done
27 | 27.27.27 | check baggage under important information | Display the baggage information | completed | completed |  |  | NOt required | TC ET 27 | Windows |  | Done
28 | 28.28.28 | check Adds on text | Display the Adds on text | completed | completed |  |  | NOt required | TC ET 28 | Windows |  | Done
29 | 29.29.29 | check all benefits | Verify the all benefits | completed | completed |  |  | NOt required | TC ET 29 | Windows |  | Done
30 | 30.30.30 | check the button | Check the conform trip button | completed | completed |  |  | NOt required | TC ET 30 | Windows |  | Done
31 | 31.31.31 | check donating button work or not | Check the thanks for donating button | completed | completed |  |  | NOt required | TC ET 31 | Windows |  | Done
32 | 32.32.32 | check continue button | Check the continue button Functionality | completed | completed |  |  | NOt required | TC ET 32 | Windows |  | Done
33 | 33.33.33 | check flight text | Display the flight text | completed | completed |  |  | NOt required | TC ET 33 | Windows |  | Done
34 | 34.34.34 | veriify the link | Check the flight details link | completed | completed |  |  | NOt required | TC ET 34 | Windows |  | Done
35 | 35.35.35 | check the traveller details txt | Display the traveller details text | completed | completed |  |  | NOt required | TC ET 35 | Windows |  | Done
36 | 36.36.36 | check Add adults | Check the Add adults functionality | completed | completed |  |  | NOt required | TC ET 36 | Windows |  | Done
37 | 37.37.37 | check the name | Check the first name and last name | completed | completed |  |  | NOt required | TC ET 37 | Windows |  | Done
38 | 38.38.38 | radio button working or not | check radio button | completed | completed |  |  | NOt required | TC ET 38 | Windows |  | Done
39 | 39.39.39 | check contact information | verify contact information | completed | completed |  |  | NOt required | TC ET 39 | Windows |  | Done
40 | 40.40.40 | check checkbox | verify checkbox for GSTbusiness travel claim | completed | completed |  |  | NOt required | TC ET 40 | Windows |  | Done
41 | 41.41.41 | check acknowledement check box | check acknowledment check box | completed | completed |  |  | NOt required | TC ET 41 | Windows |  | Done
42 | 42.42.42 | check continue button | check continue button functionality | completed | completed |  |  | NOt required | TC ET 42 | Windows |  | Done
Travels And ADD-ONS
1 | 1.1.1 | Ancillary Page | Navigate to ancillary page and defines its display objects. | Completed | Completed |  |  | Not Required | TC_AT_01, TC_AT_01, TC_AT_01 | Windows |  | Done
2 | 2.2.2 | Meal Tab With its Object | Check the Display of Meal Tab With its Object. | Completed | Completed |  |  | Not Required | TC_AT_04 | Windows |  | Done
3 | 3.3.3 | Dispaly of Non-Vegetarian food items | Check User is able to select "Non-Vegetarian Food Items"under Meal Tab with it's icon and amount. | Completed | Completed |  |  | Not Require | TC_AT_05 | Windows |  | Done
4 | 4.4.4 | Dispaly of Vegetarian food items | Check User is able to select "Vegetarian Food Items "under Meal Tab with it's icon and amount. | Completed | Completed |  |  | Not Required | TC_AT_06 | Windows |  | Done
5 | 5.5.5 | Add Button Functionality | Check user is able to enter 1 meal item | Completed | Completed |  |  | Not Required | TC_AT_07 | Windows |  | Done
|  |  | Check user is able to enter more than 1 meal item | Testing | To Do List |  |  | Not Required | TC_AT_08 | Windows |  | No | DF_020:User is Not able to SelectMore than one option
6 | 6.6.6 | Footer Section | Check the Display of Footer Section With its Object in meal section. | Completed | Completed |  |  | Not Required | TC_AT_09 | Windows |  | Done
7 | 7.7.7 | Reset Link | Check Reset Link is woking properly or not. | Completed | Completed |  |  | Not Required | TC_AT_10 | Windows |  | Done
8 | 8.8.8 | Baggage Tab With its Object | Check the Display of Baggage Tab With its Object. | Completed | Completed |  |  | Not Required | TC_AT_11 | Windows |  | Done
9 | 9.9.9 | Dispaly of "Additional 5 Kg" option | Check user is able to select "Additional 5 Kg"option under Baggage Tab with its icon and amount. | Completed | Completed |  |  | Not Required | TC_AT_12 | Windows |  | Done
10 | 10.10.10 | Dispaly of "Additional 10 Kg" option | Check user is able to select "Additional 10 Kg"option under Baggage Tab with its icon and amount. | Completed | Completed |  |  | Not Required | TC_AT_13 | Windows |  | Done
11 | 11.11.11 | Add Button Functionality | Check user is able to enter 1 baggage item | Completed | Completed |  |  | Not Required | TC_AT_14 | Windows |  | Done
12 | 12.12.12 |  | Check user is able to enter more than 1 baggage item | Testing | To Do List |  |  | Not Required | TC_AT_15 | Windows |  | Done | DF_021:User is Not able to Select More than one option
13 | 13.13.13 | Footer Section | Display of The Footer section Object | Completed | Completed |  |  | Not Required | TC_AT_16 | Windows |  | Done
14 | 14.14.14 | Continue Button functionality | Check "Continue" Button is navigating you to the next Page or not. | Completed | Completed |  |  | Not Required | TC_AT_17 | Windows |  | Done
PAYMENT GATEWAY
1 | 1.1.1 | Payment Page | Navigate to Payment page and defines its display objects. | Completed | Completed |  |  | Not Required | TC_PT_1, TC_PT_2, TC_PT_3 | Windows |  | Done
2 | 2.2.2 | Payment Option | Display The Payment Tab objects. | Completed | Completed |  |  | Not Required | TC_PT_4, TC_PT_5 | Windows |  | Done
|  |  | Check if you are able to select option under "UPI" mode of Payment. | Testing | In To Do List |  |  | Not Required | TC_PT_6 | Windows |  | Done | DF_022:User in not able to select UPI option.
|  |  | Check if you are able to select Major bank under "Net Banking" mode of Payment | Completed | Completed |  |  | Not Required | TC_PT_7 | Windows |  | Done
|  |  | Check if you are able to select option under "Mobile Wallet " mode of Payment. | Completed | Completed |  |  | Not Required | TC_PT_8 | Windows |  | Done
|  |  | Check if you are able to select option under No Cost EMI "mode of Payment. | Completed | Completed |  |  | Not Required | TC_PT_9 | Windows |  | Done
|  |  | Check if you are able to select type of money under "Paypal" mode of Payment. | Completed | Completed |  |  | Not Required | TC_PT_10 | Windows |  | Done
3 | 3.3.3 | Finish Button | Check the "Finish Payment" Button functionality. | Completed | Completed |  |  | Not Required | TC_PT_11 | Windows |  | Done
BOOKING SUMMARY
1 | 1.1.1 | Final Details of Booking Flight | Check the Final details under Successfully Booked Ticket Tab that is comprises of Flight name, Duration of journey,Time of Flight and Total price. | Completed | Completed |  |  | Not Required | TC_BT_1 | Windows |  | Done
2 | 2.2.2 | Booking Summary | Check the Book Summary Tab on the right hand side of the page. | Completed | Completed |  |  | Not Required | TC_BT_2 | Windows |  | Done
LOG-OUT
1 | 1.1.1 | verify After successfull login click on profile icon to check logout button is visible or not | Verify Logout link is working properly or not | completed | Completed |  |  | Not required | TC_Log001 | Windows |  | Done
2 | 2.2.2 | Verify logout option from by selecting 'Right coloumn' option. | Check user is able to logout option from by selecting' Right coloumn' option. | completed | Completed |  |  | Not required | TC_Log002 | Windows |  | Done
3 | 3.3.3 | Verify, the Application Login session status,after logging and closing the browser without logging out. | check the Application Login session status | completed | Completed |  |  | Not required | TC_Log003 | Windows |  | Done
4 | 4.4.4 | Verify logout option is not displayed under 'My Account'. | check logout button is displayed or not | completed | Completed |  |  | Not required | TC_Log004 | Windows |  | Done
5 | 5.5.5 | verify logout option is not displayed under 'Right Column'option before you login. | check user is able display logout option or not | completed | Completed |  |  | Not required | TC_Log005 | Windows |  | Done
6 | 6.6.6 | Verify Logout option is clickable or not | Check logout button is able clickable or not | completed | Completed |  |  | Not required | TC_Log006 | Windows |  | Done